## Quarter 1
Quarterly Olmstead Community Integration Summary
CY16 Quarter: | January 1-March 31
Agency: | Health Care Finance
Date Submitted: | 2016-04-25
Agency Director: | Wayne Turnage
Olmstead Plan Coordinator: | Leyla Sarigol
Action: | Responsible Agency: | Narrative: | Suggested Metrics: | Outcome: | % Annual Goal Met:
Transitions from LTC facilities to HCBS | DHCF | Three (3) unique enrollments in Personal Care Aide Services under the Medicaid State Plan and/or Elderly and persons with Physical Disabilities Home and Community-Based Services Waiver Program within 60 days of discharge for those Medicaid beneficiaries who were discharged from a nursing facility, January through March, 2016, after a 90+ day stay. | Unduplicated count from the transition goals of other District agencies’ Olmstead goals. | 3 new transitions in the quarter. (Total for year = 8 of 30 transitions.) | 10%
Priority Area #1: A Person-Centered Culture
Develop and implement clear expectations, competency criteria, standards, policies and protocols for all LTSS staff in the consistent use of person-centered approaches to service and planning, including using principles of supported decision-making (regardless of whether individuals have guardians or other substitute healthcare decision-makers) | NWD/DDS | DHCF is working closely with the No Wrong Door team to implement a robust training curriculum, including a person-centered thinking trainer at DHCF, conducting 2-day training for all Long Term Care and Ombudsman staff on person-centered thinking, and requiring 10 hours of on-line training across a 12-month period for each EPD-serving case manager. DHCF also continues to conduct PCP trainings, most recently of the LTC Monitoring Team and for DHCF’s long term care services and supports contractor, Delmarva Foundation.
Priority Area #2: Community Engagement, Outreach and Training
Priority Area #3: Employment
Priority Area #4: Housing
DHCF, in collaboration with DCOA’s ADRC held a lottery on February 29, 2016 for 14 available Housing Choice Vouchers to support the transition to community living for preliminarily MFP-eligible nursing facility residents. 14 residents were selected, as well as 109 alternates. DHCF updated and released the accompanying transmittal on conditions of selection (Transmittal 16-02) and FAQs on February 1, 2016. DHCF provided training for the ADRC Community Transition Team on the conditions in February 2016 ahead of the lottery.
Priority Area #5: Intake, Enrollment and Discharge Processes
|  | DHCF is proposing rules to establish standards governing the assessment process for the level of need for beneficiaries who receive Long Term Care Services and Supports (LTCSS), with the exception of Intermediate Care Facilities for Individuals with Intellectual and Developmental Disabilities (ICF/IDD) services, and Home and Community-based Waiver Services for Individuals with Intellectual and Developmental Disabilities (IDD Waiver). This includes nursing home services, supports under the Elderly and Physical Disabilities Home and Community-Based Services waiver (EPD Waiver), Personal Care Assistance (PCA) services, Adult Day Health Program (ADHP) services under the home and community-based state plan benefit, and other LTCSS not intended to service individuals with IDD. The assessment process is conducted by using a standardized needs-based assessment tool. The tool is currently being used by DHCF to assess the need for Medicaid PCA services under the State Plan and EPD Waiver. It will eventually be used to assess the need for the other long term care services described herein as the rules governing those services are amended. Hence, the effective date of the tool will be staggered to coincide with the effective date of the revised/amended EPD Waiver rules, and the revised rules governing other long term care services. | Average EPD and IDD Waiver enrollment times.
% of relevant DC agency staff and providers receiving training on HCBS services and discharge procedures.
# of public events/participants on LTSS system access and Medicaid Waiver protocols and processes.
Priority Area #6: Medicaid Waiver Management and Systems Issues
Develop training on how to access Medicaid Waiver services and troubleshooting for agency and provider staff involved in the EPD Waiver process | DHCF, ADRC, DOH | DHCF LTC Administration staff met twice during the period with representatives of the LTC and Health Care Ombudsmen’s offices, the Legal Counsel for the Elderly, and DCOA’s Aging & Disability Resource Center to discuss access to services for existing beneficiaries and new enrollees, some of whom would be transitioning from nursing facilities and other LTC facilities to the community. The discussion focused on defining services and appropriate referrals, and identifying contact points for each participating agency and program. DHCF has also involved providers and stakeholders in meetings to review and develop new business processes to streamline the waiver eligibility process.
Develop and implement a Participant Directed Program, allowing people receiving EPD Waiver services to have responsibility for managing and directing all aspects of service delivery, including who provides the services and how the services are provided | DHCF | The Participant-Directed Services (PDS) program, Services My Way, began enrollment March 28, 2016, and is anticipating that services for the first participants will begin in late April 2016. The PDS workgroup continues to advise DHCF via monthly meetings, and the PDS Program Coordinator completed individualized trainings for all case management agencies enrolled as providers in the EPD Waiver. The PDS Program Coordinator continues trainings for DHCF staff, and stakeholders, on the PDS Program.
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
Assess and reduce duplication of services offered by Medicaid and DCOA |  | DHCF and DCOA (in collaboration with ESA) have been engaged in a 6 month effort to analyze and re-engineer the workflow for individuals seeking and retaining long term care services. This workflow analysis has allowed the agencies to identify duplicative or inefficient processes and streamline access to LTC services. DHCF and DCOA have also developed plans to maximize Medicaid reimbursement for services that are currently being funded with local dollars, specifically, transportation and case management services.
Review and strengthen regulatory options to more effectively deal with quality issues when they arise | DHCF, DDS, DBH, DOH | DHCF is updating its rules for EPD waiver providers, Home Health Agencies, Adult Day Health Providers and for Provider Screening and Enrollment. DHCF has developed new protocols with DOH to foster greater collaboration and information sharing regarding personal care aides who are terminated for cause.
Review all providers’ Language Access plans to ensure residents with limited English proficiency have access to linguistically and culturally appropriate services | DHCF and DDS | DHCF was recently classified as an agency with “major public contact”, and therefore included on the Office of Human Rights’ (OHR) efforts around maintaining and monitoring departmental language access plans, per the DC Language Access Act. DHCF’s Medicaid Director has convened a workgroup of staff representing each division within DHCF to develop the Department’s Bi-Annual Language Access Plan, due to OHR October 2016. The workgroup is meeting every two weeks, and is working towards efforts including • Submit/implement/monitor 2 year language access plan (next cycle—FY17/18) • Designate a DHCF language access coordinator • Documented community outreach re language access As part of these efforts, DHCF is focusing on: • Defining DHCF-specific threshold languages (>3% of population or 500 ppl) • Data collection • Staff training • Providing translation (DHCF must translate all “vitals documents” into the threshold languages) • Providing interpretation
Priority Area #8: Supporting Children and Youth
Priority Area #9: Wellness and Quality of Life
Note on C8: ServUS: How did you agency arrive at this number? Please outline any challenges or best practices.

## Quarter 2
Quarterly Olmstead Community Integration Summary
CY16 Quarter: | April 1-June 30
Agency: | Health Care Finance
Date Submitted: | 2016-07-15
Agency Director: | Wayne Turnage
Olmstead Plan Coordinator: | Leyla Sarigol
Action: | Responsible Agency: | Narrative: | Suggested Metrics: | Outcome: | % Annual Goal Met:
Transitions from LTC facilities to HCBS | DHCF | Five (5) unique enrollments in Personal Care Aide Services under the Medicaid State Plan and/or Elderly and persons with Physical Disabilities Home and Community-Based Services Waiver Program within 60 days of discharge for those Medicaid beneficiaries who were discharged from a nursing facility or hospital, April through June, 2016, after a 90+ day stay. | Unduplicated count from the transition goals of other District agencies’ Olmstead goals. | 5 new transitions in the quarter. (Total for year = 8 of 30 transitions.) | 26%
Priority Area #1: A Person-Centered Culture
Develop and implement clear expectations, competency criteria, standards, policies and protocols for all LTSS staff in the consistent use of person-centered approaches to service and planning, including using principles of supported decision-making (regardless of whether individuals have guardians or other substitute healthcare decision-makers) | NWD/DDS | All LTCA staff are required to attend the 2-day training and have either attended or registered (training runs monthly through September). In addition, LTCA has tapped two PCT Leads for the Administration, who have gone through the PC train the trainer.
Priority Area #2: Community Engagement, Outreach and Training
test
test
Priority Area #3: Employment
Priority Area #4: Housing
In follow up to the February 29, 2016 Money Follows the Person housing voucher lottery, DHCF continues collaboration with the DC Housing Authority and DCOA to ensure that selected nursing facility residents move through the eligibility and housing identification processes in keeping with the policies outlined in DHCF transmittal 16-02.
D
Priority Area #5: Intake, Enrollment and Discharge Processes
Average EPD and IDD Waiver enrollment times
% of relevant DC agency staff and providers receiving training on HCBS services and discharge procedures.
# of public events/participants on LTSS system access and Medicaid Waiver protocols and processes.
Priority Area #6: Medicaid Waiver Management and Systems Issues
Develop training on how to access Medicaid Waiver services and troubleshooting for agency and provider staff involved in the EPD Waiver process | DHCF, ADRC, DOH | DHCF and DCOA partnered to design a training for DCOA Citywide Case Management Agencies over the past quarter. In April, DCOA case managers were trained on how to access the EPD Medicaid Waiver, eligibility requirements and provided the documents necessary for enrollment in lieu of utilizing a Medicaid Enrollment Specialist. The goal of this training was to ensure DCOA case managers had up-to-date enrollment and eligibility information and to reduce wait times for EPD Waiver enrollment. Also in April, DHCF and DCOA conducted training at an AARP event on transitions from nursing facilities to the EPD Waiver and what steps need to be followed and what needs to be incorporated in the discharge plan to ensure a successful discharge into the community. DHCF continues to host monthly provider meetings for both EPD Waiver and ADHP providers. These meetings provide ongoing training around service delivery, applicable regulations, and updates to the EPD Waiver program. It is also a forum in which providers can bring their concerns and questions and have them addressed by DHCF staff. In May, DHCF launched an information session designed for prospective and re-enrolling providers. This is a partnership between DHCF’s Long Term Care Administration and Division of Public and Private Provider Services ensures both prospective and re-enrolling providers are aware of the regulations that govern the EPD Waiver and Medicaid program, the basic tenets of the EPD Waiver program to include the 6 CMS assurances and person-centered thinking, service delivery and requirements to be considered a qualified Medicaid Waiver provider. Two provider information sessions were held during this quarter. DHCF is currently developing a new provider orientation to provide education around the roles and responsibilities of case management agencies to include eligibility, person-centered planning, service delivery, care coordination, crisis intervention, documentation, timely recertification, transfer of services, change requests, and discharges. As new case management agencies have been approved over the past quarter, they have attended CaseNet training as well as have met individually with their EPD Waiver Team Lead for technical assistance and training as a new EPD Waiver case management provider. June 1 DHCF hosted a public forum on the EPD Waiver renewal in which staff presented the plan for the EPD Waiver renewal and responded to advocates’ inquiries and comments on the renewal. DHCF LTCA staff continue to actively respond to beneficiary, provider and advocate inquiries and concerns as they arise via in-person, phone, or by email and work to resolve issues timely and comprehensively.
Develop and implement a Participant Directed Program, allowing people receiving EPD Waiver services to have responsibility for managing and directing all aspects of service delivery, including who provides the services and how the services are provided | DHCF | Since Participant Directed Services (PDS) launched, the program received 84 Person-Centered Plans (PCPs) that have included Services My Way (SMW). 6 PCP's are on hold and have not been sent to DHCF's PDS contractor due to a variety of reasons.The program is either waiting for Delmarva assessments and/or there is missing or incorrect information in the PCP. 5 people opted out of SMW after meeting with DHCF's PDS contractor. 12 people are receiving SMW and have prior authorizations. DHCF continues to convene its SMW stakeholder group monthly. The rules and regulations for SMW were adopted May 11, 2016. The public comment period closed on June 20, 2016, the Division of Regulation and Policy Management is in the processing of reviewing and responding to the public comments that were submitted.
% decrease in average length of IDD and EPD Waiver application processes.
% of cases for which intake processes are followed 100% of the time.
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
Assess and reduce duplication of services offered by Medicaid and DCOA | DHCF and DCOA | DHCF concluded its workflow analysis effort in June 2016, and will spend the next six month working on implementation with a January 2017 roll-out of the changes resulting from the workflow analysis. As a “side benefit,” DHCF and its partners accomplished the following: created definition of a “complete” Medicaid application; developed a new Prescription Order Form to request long term care services and supports; developed a new LTC assessment determination form; streamlined the transition from nursing home to the community.
Review and strengthen regulatory options to more effectively deal with quality issues when they arise | DHCF, DDS, DBH, DOH | The pending EPD waiver rules will allow DHCF to provide better oversight and monitoring to ensure that quality services in conjunction with CMS’ community integration mandates are delivered and monitored. Similar changes have been made to DBH’S, and DDS’ rules and wilwill be made to DOH’s rules. All these changes will cumulatively allow DHCF to more effectively monitor and address issues around quality. DHCF is updating its rules for EPD waiver providers, Home Health Agencies, Adult Day Health Providers and for Provider Screening and Enrollment. DHCF has developed new protocols with DOH to foster greater collaboration and information sharing regarding personal care aides who are terminated for cause.
Review all providers’ Language Access plans to ensure residents with limited English proficiency have access to linguistically and culturally appropriate services | DHCF and DDS | Ongoing--DHCF continues to develop it's Bi-Annual Language Access Plan, which will be submitted to OHR this summer for review and finalized before October 1, 2016
|  | Re: ADHP recertification. Provider enrollments began in the last quarter of FY15. Annual provider re-certifications will begin in the last quarter of FY16. | #/% of adult day health recertifications completed within designated timeframes.
% of people who receive the services for which they have been assessed/referred.
% of mandatory, annual HBCS training requirements that providers meet.
Priority Area #8: Supporting Children and Youth
Priority Area #9: Wellness and Quality of Life
#/% of medical professionals using the medical home primary care model.
#/% of inclusive daytime program offerings.
#/% of people with disabilities using various transportation mechanisms.
Note on C8: ServUS: How did you agency arrive at this number? Please outline any challenges or best practices.

## Quarter 3
Quarterly Olmstead Community Integration Summary
CY16 Quarter: | July 1- September 30
Agency: | Health Care Finance
Date Submitted: | 10/25/2016 (Version 2. Version 1 submitted 10/24/16)
Agency Director: | Wayne Turnage
Olmstead Plan Coordinator: | Leyla Sarigol
Action: | Responsible Agency: | Narrative: | Suggested Metrics: | Outcome: | % Annual Goal Met:
Transitions from LTC facilities to HCBS | DHCF | Nineteen (19) unique enrollments in and/or claims for Personal Care Aide Services, Skilled Nursing, or Adult Day Health Program under the Medicaid State Plan and/or Elderly and persons with Physical Disabilities Home and Community-Based Services Waiver Program within 60 days of discharge for those Medicaid beneficiaries who were discharged from a nursing facility or hospital, July through September, 2016, after a 90+ day stay. | Unduplicated count from the transition goals of other District agencies’ Olmstead goals. | 19 new transitions in the quarter. (Total for year = 27 of 30 transitions.) | 90%
Priority Area #1: A Person-Centered Culture
Develop and implement clear expectations, competency criteria, standards, policies and protocols for all LTSS staff in the consistent use of person-centered approaches to service and planning, including using principles of supported decision-making (regardless of whether individuals have guardians or other substitute healthcare decision-makers) | NWD/DDS | Twenty-five (25) of twenty-nine (29) LTCA staff attended the 2-day training. Two (2) of the four (4) remaining staff will take the training in October 2016, and the other two (2) are pending registration. The two (2) PCT leads for the LTCA who completed the PC train the trainer program led two (2) PCT sessions during the quarter, and are expected to lead a third in October 2016 .
Priority Area #2: Community Engagement, Outreach and Training
test
test
Priority Area #3: Employment
Priority Area #4: Housing
|  | In follow up to the February 29, 2016 Money Follows the Person housing voucher lottery, DHCF continues collaboration with the DC Housing Authority and DCOA to ensure that selected nursing facility residents move through the eligibility and housing identification processes in keeping with the policies outlined in DHCF transmittal 16-02. It is anticipated that all selected nursing facility residents will use vouchers by December 31, 2016. | In follow up to the February 29, 2016 Money Follows the Person housing voucher lottery, DHCF continues collaboration with the DC Housing Authority and DCOA to ensure that selected nursing facility residents move through the eligibility and housing identification processes in keeping with the policies outlined in DHCF transmittal 16-02. It is anticipated that all selected nursing facility residents will use vouchers by December 31, 2016. As of September 30th, nine (9) of the fourteen (14) selected candidates had progressed to lease signing and voucher issuance.
D
Priority Area #5: Intake, Enrollment and Discharge Processes
Average EPD and IDD Waiver enrollment times*
% of relevant DC agency staff and providers receiving training on HCBS services and discharge procedures.**
# of public events/participants on LTSS system access and Medicaid Waiver protocols and processes.**
Priority Area #6: Medicaid Waiver Management and Systems Issues
Develop training on how to access Medicaid Waiver services and troubleshooting for agency and provider staff involved in the EPD Waiver process | DHCF, ADRC, DOH | • DHCF presented at Department of Behavioral Health on August 25, 2016 to the MHRS Provider Clinical Directors’ meeting. DHCF provided education regarding the EPD Waiver program and how to access services. • DHCF LTCA staff continue to actively respond to beneficiary, provider and advocate inquiries and concerns as they arise via in-person, phone, or by email and work to resolve issues timely and comprehensively. • DHCF conducted three (3) provider meetings for EPD Waiver providers during the quarter (7/21/2016, 8/18/2016, 9/15/2016). • DHCF convened prospective provider enrollment sessions in July and August 2016. • Selection panel for the Clinical Case Management System (composed of staff from DHCF, DDS and DCOA) met several times over the quarter to select a vendor. The package is now under OCP review and will be sent to Council. It is anticipated vendor will on-board in April, 2017. CCMS will create a system for real time communication amongst agencies and minimize the duplication of information sharing for beneficiaries. It will also increase transparency of applications moving through the system. • This quarter, the ADRC convened a discharge planning workgroup in July 2016 to outline the discharge planning process for individuals who are trying to access HCBS upon discharge from a nursing facility or hospital. DHCF participated in these workgroups and provided content for the discharging planning manual. The manual is under development.
Develop and implement a Participant Directed Program, allowing people receiving EPD Waiver services to have responsibility for managing and directing all aspects of service delivery, including who provides the services and how the services are provided | DHCF | The Participant directed Services (PDS) program, known as Services My Way (SMW) began enrollment on March 28, 2016. The program has received 219 Person-Centered Plans (PCPs) that have included SMW. There are currently 75 participants that are accessing SMW. Fourteen (14) people opted out after receiving more information about the program. And, the remaining 130 are anticipated to enroll in SMW once their PCP review is complete. DHCF provides monthly trainings to case management agencies and continues to convene monthly stakeholder meetings. The first Emergency and Proposed SMW rules and regulations were adopted May 11, 2016. DHCF received public comments and took careful consideration to all comments; as a result the Division of Regulation and Policy Management made significant changes to the 2nd Emergency and Proposed Rules and Regulations. DHCF is currently in the process of publishing the 2nd Emergency and Proposed SMW rules and regulations.
% decrease in average length of IDD and EPD Waiver application processes.**
% of cases for which intake processes are followed 100% of the time. **
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
Assess and reduce duplication of services offered by Medicaid and DCOA | DHCF and DCOA | • DHCF concluded its workflow analysis effort in June 2016, and will spend the next six month working on implementation with a January 2017 roll-out of the changes resulting from the workflow analysis. As a “side benefit,” DHCF and its partners accomplished the following: created definition of a “complete” Medicaid application; developed a new Prescription Order Form to request long term care services and supports; developed a new LTC assessment determination form; streamlined the transition from nursing home to the community. •DHCF, DCOA, Seabury Resources for the Aging, and the Non-Emergency Medical Transportation (NEMT) Broker, Medical Transportation Management, Inc. (MTM) implemented an action plan to enroll Seabury Resources for the Aging as a transportation provider in the DC NEMT network. The focus of the action plan was to remove a duplication of non-emergency medical transportation services provided by Seabury and MTM. Seabury Resources for the Aging will receive reimbursement directly from MTM for non-emergency transportation services for 1,008 DC Medicaid Fee for Service (FFS) beneficiaries who utilize Seabury for transportation services to and from health care appointments. • DHCF is also working to enroll DCOA lead agencies as EPD waiver case managers. To date, six (6) DCOA lead agencies submitted applications. Those applications are under review by DHCF.
Review and strengthen regulatory options to more effectively deal with quality issues when they arise | DHCF, DDS, DBH, DOH | The District is in the final stages of publishing its EPD Waiver Regulations. A legal sufficiency certificate was received on September 29th, and the rules are in its final stages of review at the Executive Office of the Mayor before it goes to the Office of Documents and Administrative Issuances (ODAI) for publication in the D.C. Register. | Publication of Chapter 42 rules governing the EPD Waiver program in the D.C. Register
Review all providers’ Language Access plans to ensure residents with limited English proficiency have access to linguistically and culturally appropriate services | DHCF and DDS | OHR approved DHCF’s proposed FY17-18 Bi-annual Language Access Plan (BLAP). DHCF is developing a training for all Medicaid providers on the requirements behind the DC Language Access Act, which is expected to be introduced in phases in the latter part of FY2017. In addition, the following items are included in the plan: • With regards to DHCF’s Long Term Care Administration (LTCA), staff review and approve agency policies and procedures through its provider readiness process during initial enrollment and reenrollment. • Subsequent to enrollment as a provider, LTCA conducts routine monitoring of entities providing long term care services and supports. The indicator used to verify the language access policy is whether the provider policies and procedures includes provisions for LEP/NEP beneficiaries to receive adequate services and identify the resources necessary to support their care, including referring the recipient to provider with specific LEP/NEP capacity. • Additionally, the LTCA monitoring team reviews on an annual basis whether the provider has a plan to adequately serve LET/NEP speaking recipients that includes timely referral to an appropriate resource to accommodate recipient's language needs.
|  | Re: ADHP recertification. Provider enrollments began in the last quarter of FY15. As moderate risk providers, re-certifications occur every five (5) years. | #/% of adult day health recertifications completed within designated timeframes. Note: Provider enrollment began in FY15. The first recertification will be FY20.
% of people who receive the services for which they have been assessed/referred. **
% of mandatory, annual HBCS training requirements that providers meet. **
Priority Area #8: Supporting Children and Youth
Priority Area #9: Wellness and Quality of Life
#/% of medical professionals using the medical home primary care model. **
#/% of inclusive daytime program offerings.**
#/% of people with disabilities using various transportation mechanisms. **
*Data collected by enrollment agencies for these HCBS Waivers. DCOA-EPD Waiver. DDS-IDD Waiver.
**Methodology for the suggested metric is under discussion.

## Quarter 4
Quarterly Olmstead Community Integration Summary
CY16 Quarter: | October 1-December 31
Agency: | Health Care Finance
Date Submitted: | 2017-02-02
Agency Director: | Wayne Turnage
Olmstead Plan Coordinator: | Leyla Sarigol
Action: | Responsible Agency: | Narrative: | Suggested Metrics: | Outcome: | % Annual Goal Met:
Transitions from LTC facilities to HCBS | DHCF | Four (4) unique enrollments in and/or claims for Personal Care Aide Services, Skilled Nursing, or Adult Day Health Program under the Medicaid State Plan and/or Elderly and persons with Physical Disabilities Home and Community-Based Services Waiver Program within 60 days of discharge for those Medicaid beneficiaries who were discharged from a nursing facility or hospital, October through December, 2016, after a 90+ day stay. | Unduplicated count from the transition goals of other District agencies’ Olmstead goals. | 4 new transitions in the quarter. (Total for year = 31 of 30 transitions.) | 103%
Priority Area #1: A Person-Centered Culture
Develop and implement clear expectations, competency criteria, standards, policies and protocols for all LTSS staff in the consistent use of person-centered approaches to service and planning, including using principles of supported decision-making (regardless of whether individuals have guardians or other substitute healthcare decision-makers) | NWD/DDS | Thirty-two (32) of thirty-five (35) LTCA staff attended the 2-day training. The three (3) remaining staff and additional recent hires are pending registration. The two (2) PCT leads for the LTCA who completed the PC train-the-trainer program led three (3) PCT sessions to date.
Priority Area #2: Community Engagement, Outreach and Training
Priority Area #3: Employment
Priority Area #4: Housing
In follow up to the February 29, 2016 Money Follows the Person housing voucher lottery, DHCF continues collaboration with the DC Housing Authority and DCOA to ensure that selected nursing facility residents move through the eligibility and housing identification processes in keeping with the policies outlined in DHCF transmittal 16-02. It is anticipated that all selected nursing facility residents will use vouchers in 2017. As of December 31st, eight (8) of the fourteen (14) selected candidates had progressed to lease signing and voucher issuance. In addition, due to attrition of program participants, five (5) additional vouchers became available and have been offered to alternates selected in the lottery who are in various stages of the voucher eligibility and housing search process.
Priority Area #5: Intake, Enrollment and Discharge Processes
Average EPD and IDD Waiver enrollment times*
% of relevant DC agency staff and providers receiving training on HCBS services and discharge procedures.**
# of public events/participants on LTSS system access and Medicaid Waiver protocols and processes.**
Priority Area #6: Medicaid Waiver Management and Systems Issues
Develop training on how to access Medicaid Waiver services and troubleshooting for agency and provider staff involved in the EPD Waiver process | DHCF, ADRC, DOH | • On October 13, 2016, DHCF Long Term Care Administration (LTCA) and Policy staff met with AARP Ombudsman and provided a training on HCBS Spend down • On October 20, 2016, DHCF LTCA convened an information fair for beneficiaries of the Elderly and persons with Physical Disabilities (EPD) Waiver program. The fair gave program participants an opportunity to meet Medicaid enrolled EPD providers, and learn more about the services they offer. DHCF staff also provided information about the continuum of Medicaid HCBS available to them. • DHCF LTCA staff participated in October and December 2016 meetings of the DC Long Term Care Coalition. LTC HCBS updates were provided to coalition members. • DHCF’s LTCA convened a regular meeting of Medicaid-enrolled EPD and State Plan Home Health providers on November 17, 2016. During the meeting, DHCF staff shared important HCBS programmatic and policy updates. • On December 15, 2016, DHCF LTCA and Policy staff met with nursing facility providers at Carroll Manor to provide education on the revised LTC Medicaid application. | d
Develop and implement a Participant Directed Program, allowing people receiving EPD Waiver services to have responsibility for managing and directing all aspects of service delivery, including who provides the services and how the services are provided | DHCF | The District’s Participant-Directed Services (PDS) program, known as Services My Way (SMW) began enrollment on March 28, 2016. The program is a service for people enrolled in the Elderly and persons with Physical Disabilities (EPD) Waiver Program. The Program has received 331 Person-Centered Plans (PCPs) that have included SMW. There are currently 131 participants that are accessing SMW. DHCF provides monthly trainings to case management agencies and continues to convene monthly stakeholder meetings. The first Emergency and Proposed SMW rules and regulations were adopted May 11, 2016. DHCF received public comments and took careful consideration to all comments; as a result the Division of Regulation and Policy Management made significant changes to the 2nd Emergency and Proposed Rules and Regulations. The 2nd Emergency and Proposed SMW rules and regulations were adopted on November 22, 2016. Increasingly, DC's Money Follows the Person participants transitioning from nursing facilities to HCBS are exploring SMW as an option for personal care services. To date, three MFP participants (one current, two former) have successfully enrolled in SMW.
% decrease in average length of IDD and EPD Waiver application processes.**
% of cases for which intake processes are followed 100% of the time. **
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
Assess and reduce duplication of services offered by Medicaid and DCOA | DHCF and DCOA | DHCF and DCOA meet monthly to streamline DCOA’s function as the front door to DHCF’s long term care services.
Review and strengthen regulatory options to more effectively deal with quality issues when they arise | DHCF, DDS, DBH, DOH | The initial emergency and proposed rulemaking governing the EPD Waiver program was published in the D.C. Register on November 4th, 2016. DHCF received one set of comments on the rulemaking, and has incorporated changes addressing the comments received, as well as changes incorporating provisions of the EPD Waiver renewal, into the second emergency and proposed rulemaking. The second emergency and proposed rulemaking is currently under executive-level agency review and DHCF anticipates publication prior to the April 4, 2017 effective date of the EPD Waiver renewal. This second ER and Proposed rule incoporates intermediate sanctions for providers who fail to comply with the standards for service delivery. | Publication of Chapter 42 rules governing the EPD Waiver program in the D.C. Register
Review all providers’ Language Access plans to ensure residents with limited English proficiency have access to linguistically and culturally appropriate services | DHCF and DDS | OHR approved DHCF’s proposed FY17-18 Bi-annual Language Access Plan (BLAP). DHCF is developing a training for all Medicaid providers on the requirements behind the DC Language Access Act, which is expected to be introduced in phases in the latter part of FY2017. In the first quarter of FY2017, DHCF engaged in ongoing monitoring of LTC providers, which included review of policies and procedures specific to language access
|  | Re: ADHP recertification. Provider enrollments began in the last quarter of FY15. As moderate risk providers, re-certifications occur every five (5) years. | #/% of adult day health recertifications completed within designated timeframes. Note: Provider enrollment began in FY15. The first recertification will be FY20.
% of people who receive the services for which they have been assessed/referred. **
% of mandatory, annual HBCS training requirements that providers meet. **
Priority Area #9: Wellness and Quality of Life
#/% of medical professionals using the medical home primary care model. **
#/% of inclusive daytime program offerings.**
#/% of people with disabilities using various transportation mechanisms. **
*Data collected by enrollment agencies for these HCBS Waivers. DCOA-EPD Waiver. DDS-IDD Waiver.
**Methodology for the suggested metric is under discussion.
Note on C8: ServUS: How did you agency arrive at this number? Please outline any challenges or best practices.

## CY17 Quarter 1
Quarterly Olmstead Community Integration Summary
CY17 Quarter: | January 1- March 31
Agency: | Health Care Finance
Date Submitted: | 2017-05-31
Agency Director: | Wayne Turnage
Olmstead Plan Coordinator: | Leyla Sarigol
Action: | Responsible Agency: | Narrative: | Suggested Metrics: | Outcome: | % Annual Goal Met:
Transitions from LTC facilities to HCBS | DHCF | Eleven (11) unique enrollments in and/or claims for Personal Care Aide Services, Skilled Nursing, or Adult Day Health Program under the Medicaid State Plan and/or Elderly and persons with Physical Disabilities Home and Community-Based Services Waiver Program within 60 days of discharge for those Medicaid beneficiaries who were discharged from a nursing facility or hospital, October through December, 2016, after a 90+ day stay. | Unduplicated count from the transition goals of other District agencies’ Olmstead goals. | 11 new transitions in the quarter. (Total for year = 11 of 30 transitions.) | 36%
Priority Area #1: A Person-Centered Culture
Develop and implement clear expectations, competency criteria, standards, policies and protocols for all LTSS staff in the consistent use of person-centered approaches to service and planning, including using principles of supported decision-making (regardless of whether individuals have guardians or other substitute healthcare decision-makers) | NWD/DDS | All thirty-five (35) LTCA staff attended the 2-day training. The two (2) PCT leads for the LTCA who completed the PC train-the-trainer program led three (3) PCT sessions to date. DHCF continues to work with NWD partner agencies to assure that 100% of enrolled providers and staff complete the training.
Priority Area #2: Community Engagement, Outreach and Training
Priority Area #3: Employment
Priority Area #4: Housing
In follow up to the February 29, 2016 Money Follows the Person housing voucher lottery, DHCF continues collaboration with the DC Housing Authority and DCOA to ensure that selected nursing facility residents move through the eligibility and housing identification processes in keeping with the policies outlined in DHCF transmittal 16-02. It is anticipated that all selected nursing facility residents will use vouchers in 2017. As of March 31st, nine (9) of the fourteen (14) selected candidates had progressed to lease signing and voucher issuance. In addition, due to attrition of program participants, five (5) additional vouchers became available and have been offered to alternates selected in the lottery who are in various stages of the voucher eligibility and housing search process.
Priority Area #5: Intake, Enrollment and Discharge Processes
Average EPD and IDD Waiver enrollment times*
% of relevant DC agency staff and providers receiving training on HCBS services and discharge procedures.**
# of public events/participants on LTSS system access and Medicaid Waiver protocols and processes.**
Priority Area #6: Medicaid Waiver Management and Systems Issues
Develop training on how to access Medicaid Waiver services and troubleshooting for agency and provider staff involved in the EPD Waiver process | DHCF, ADRC, DOH | During the quarter, DHCF convened monthly meetings with EPD Waiver and State Plan providers. | d
Develop and implement a Participant Directed Program, allowing people receiving EPD Waiver services to have responsibility for managing and directing all aspects of service delivery, including who provides the services and how the services are provided | DHCF | The District’s Participant-Directed Services (PDS) program, known as Services My Way (SMW) began enrollment on March 28, 2016. The program is a service for people enrolled in the Elderly and persons with Physical Disabilities (EPD) Waiver Program. The Program has received 552 Person-Centered Plans (PCPs) that have included SMW. There are currently 258 participants that are accessing SMW. DHCF provides monthly trainings to case management agencies and continues to convene monthly stakeholder meetings. The initial emergency and proposed rules governing the Services My Way program were adopted on May 11, 2016 and published on May 20, 2016. DHCF received several sets of public comments on the initial rulemaking and incorporated revisions based on the comments into the second emergency and proposed rules, which were adopted on November 22, 2016 and published on December 9, 2016. Although no comments were received on the second emergency and proposed rules, DHCF is required to promulgate a third emergency and proposed rulemaking in order to incorporate changes from the approved EPD Waiver renewal. The third emergency and proposed rules are currently under review by EOM. Increasingly, DC's Money Follows the Person participants transitioning from nursing facilities to HCBS are exploring SMW as an option for personal care services. To date, three MFP participants (one current, two former) have successfully enrolled in SMW.
% decrease in average length of IDD and EPD Waiver application processes.**
% of cases for which intake processes are followed 100% of the time. **
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
Assess and reduce duplication of services offered by Medicaid and DCOA | DHCF and DCOA | DHCF and DCOA continue to meet monthly to streamline DCOA’s function as the front door to DHCF’s long term care services.
Review and strengthen regulatory options to more effectively deal with quality issues when they arise | DHCF, DDS, DBH, DOH | The initial emergency and proposed rulemaking governing the EPD Waiver program was published in the D.C. Register on November 4th, 2016. DHCF received one set of comments on the rulemaking, and incorporated changes addressing the comments received, as well as changes incorporating provisions of the EPD Waiver renewal, into the second emergency and proposed rulemaking, which was published on April 14, 2017. The second emergency and proposed rule incoporates intermediate sanctions for providers who fail to comply with the standards for service delivery. DHCF received one set of comments on the second emergency and proposed rule, and is currently reviewing the comments received to determine whether futher revisions to the rule are necessary. | Publication of Chapter 42 rules governing the EPD Waiver program in the D.C. Register
Review all providers’ Language Access plans to ensure residents with limited English proficiency have access to linguistically and culturally appropriate services | DHCF and DDS | In the FY16 Language Access Compliance report released by the Mayor in May 2017, DHCF received an overall score of 11 out of 12 overall compliance score, with a 3/4 for preparedeness (DHCF reported encounters with LEP/NEP customers, worked on improvements in data collection, and provided compliance training for all staff); a 5/5 for accessibility (DHCF produced 16 translated documents into Spanish and Amharic, uploaded translated documents on its website, and promoted services through diverse media outlets); and a 3/3 for quality (No complaints were filed against DHCF in FY16, and the agency was not tested). DHCF continues to implement its FY17-18 BLAP.
|  | Re: ADHP recertification. Provider enrollments began in the last quarter of FY15. As moderate risk providers, re-certifications occur every five (5) years. | #/% of adult day health recertifications completed within designated timeframes. Note: Provider enrollment began in FY15. The first recertification will be FY20.
% of people who receive the services for which they have been assessed/referred. **
% of mandatory, annual HBCS training requirements that providers meet. **
Priority Area #9: Wellness and Quality of Life
#/% of medical professionals using the medical home primary care model. **
#/% of inclusive daytime program offerings.**
#/% of people with disabilities using various transportation mechanisms. **
*Data collected by enrollment agencies for these HCBS Waivers. DCOA-EPD Waiver. DDS-IDD Waiver.
**Methodology for the suggested metric is under discussion.
Note on C8: ServUS: How did you agency arrive at this number? Please outline any challenges or best practices.