## Olmstead Report CY17 Q4
Quarterly Olmstead Community Integration Summary
CY17 Quarter: | 4
Agency: | DDS
Due Date: | 2018-02-28
Agency Director: | Andrew Reese
Olmstead Plan Coordinator: | Ed Bynum
Priority Area: | Year 1 Goal | Narrative: Quarter 1 | Narrative: Quarter 2 | Narrative: Quarter 3 | Narrative: Quarter 4 | Suggested Metrics: | Outcome: | Target
Priority Area #1: A Person-Centered Culture
Action #1: Develop and Implement Person-Centered Policies Across All NWD Core LTSS Agencies. | Develop and recommend clear expectations and competency criteria standards for intake staff consistent with use of person-centered approaches (NWD) | No Wrong Door team with subject matter experts drafted expectations and competency standards for intake staff related to the consistent use of person-centered approaches using existing models from core LTSS agencies and will be vetted by stakeholders. | The NWD project team shared expectations and competency standards for intake staff with all NWD Core LTSS agencies as well as with community partners and the DC Learning Community for Person-Centered Practices April and June meetings. The NWD inter-agency Person-Centered Practices subcommittee is scheduled to review feedback from the Learning Community next quarter. | The Person-Centered Practices Subcommittee reviewed feedback and is identifying agency priorities for implementation pending Leadership Council approval. | Completed. Core competency criteria was presented to the NWD Leadership Council and made available through agency-specific person-centered thinking policy and practices reports. Each core partner agency leadership teams will work to implement according to their respective agency priorities and agency performance standards. Expectations for person-centered thinking trainers have also been shared with agency leadership and 3 out of 3 agencies that have added person-centered SMART goals for designated PCT trainers certified through No Wrong Door. | • #/% of core LTSS agencies that have implemented person-centered service protocols. | 3 of 5 agencies | 1
[6 empty] | # of NWD Core LTSS intake staff that have completed person-centered training. | Q4, 13 of 42 learners self identified as "front line intake staff." WAITING ON CONFIRMATION OF DDS NUMBERS | Baseline
Action Step #2: Add person-centered practice standards to service planning personnel’s employee performance goals in all NWD Core LTSS agencies. | Develop a model of person-centered practice standards and goals that can be incorporated into employee performance measures. (NWD) | No Wrong Door team with subject matter experts drafted Person-centered practice standards and example employee performance measures. Will be vetted by inter-agency workgroup and NWD Leadership Council. | The NWD project team shared model of person centered practice standards and goals that can be incorporated into employee performance measures with all NWD Core LTSS agencies. | The Person-Centered Practices Subcommittee reviewed feedback and is identifying agency priorities for implementation pending Leadership Council approval. I | Completed. Model of person-centered practice standards and SMART goals that can be incorporated into employee performance goals was presented to the NWD Leadership Council and made available through agency-specific person-centered thinking policy and practices reports. | % of NWD LTSS Core Agencies’ employee performance measures linked to person-centered practices | As we are still developing a method to uniformly collect this data-there is no data to measure yet--recommended as a CY18 goal. | 75
[6 empty] | % of HCBS providers employee performance measures linked to person-centered practices | We recommend removing this metric as this data is not currently being collected by providers. | 75
Action #3: Develop procedures and protocols for supporting family members and others in a person’s support network to ensure that plans accurately and continuously reflect the individual’s preferences and needs. (NWD) | Develop Person Centered Planning Implementation Guidance’ in partnership with stakeholders identifying best practices for supporting families in person-centered planning for NWD Core LTSS agencies and providers. (NWD) | In development with stakeholder groups and community partners facilitating the Family’s Planning Together Workshops. No Wrong Door outreach team is assisting with the creation of person-centered outreach and referral information and person-centered planning tools and translation into Spanish and Amharic. | The NWD project team gathered additional input about stakeholder experiences accessing LTSS that included families and frontline support professionals across LTSS. This information, will inform best practices for supporting families from intake to planning. NWD team also regularly participates in events and learning opportunities with both the DC and the national Supporting Families of People with Intellectual and Developmental Disabilities Community of Practice. DDS, one of the NWD Core LTSS agencies, has implemented the Supporting Families LifeCourse framework into its intake process and is adding it to the annual person centered planning process as well. | NWD project team members completed the Supporting Families Lifecourse Ambassador training series to develop expertise in the supporting families framework. This will assist partners interested in implementing LifeCourse tools. NASDDDS completed a family-centered practice analysis of 4 core partner agencies to be shared with Leadership Council in Quarter 4. The analysis consisted of key informant Interviews with leadership, a paper level analysis and a summary report. | NWD project team members in collaboration with national subject matter expert drafted an analysis on family centered practices. Analysis was shared with trainers of the family planning workshop for feedback.
Priority Area #2: Community Engagement, Outreach and Training
Action #1: Develop and disseminate policy and protocols to increase linguistically and culturally diverse stakeholder involvement in the development, implementation and ongoing evaluation of NWD core LTSS agencies' engagement and outreach activities | Develop and finalize an assessment of linguistic and cultural competence for NWD Core LTSS agencies intake processes. (NWD) | DDS, DHCF, DBH, DCOA and DHS previously engaged in an analysis of current approaches to linguistic and cultural competency and recommendations for cross-agency improvements. Based upon the results of the assessment the NWD inter-agency cultural and linguistic competency work group was formed. Throughout the last quarter, the NWD CLC workgroup has drafted a definition for cultural and linguistic competency to be applied across the NWD partner agencies for intake/referral and outreach/engagement. | The NWD inter-agency cultural and linguistic competency work group finalized a definition for cultural and linguistic competency to be shared across NWD partner agencies and to be used as a lens in approaching policies, practices, and resources. The NWD Leadership Council approved the definition. The next quarter involves applying the CLC definition and framework to policies, practices, administration, and resources. To bring additional technical support, training opportunities and resources to this issue, the DDS, with support of the NWD team, applied to participate in the National Community of Practice for Cultural and Linguistic Competency. DC is one of 10 states to be selected to participate. Additionally, both DDS and DBH had an employee selected to participate in the national Leadership Institute for Cultural and Linguistic Competency. | The NWD CLC Subcommittee continues to meet monthly with representation from DBH, DHS, DDS (DDS & RSA), DCOA, DD Council (waiting on new Exec. Director), DC Interagency Council on the Homelessness, Mayor's Office on national subject matter experts to support efforts in embedding CLC within policies, structures, practices, attitudes and behaviors within partnering NWD agencies. Members of the CLC Subcommittee are also participating in the DC Community of Practice on Cultural and Linguistic Competency in Developmental Disabilities which will involve a large component of stakeholder engagement with Project ACTION!, Supporting Family Community of Practice, Person/Family-Centered Learning Community, and Provider Coalition. The NWD Door initiative hosted an inter-agency front door summit approximately 73 Front Door staff across six District health and human service agencies and the Mayor's Office on Veterans Affairs where they gained knowledge on national best practices on Cultural and Linguistic Competence to enhance the front door experience for people in need of long-term services and supports. Through the NWD initiative, the August NWD newsletter was solely focused on Cultural and Linguistic Competence which was disseminated to over 1,000 recipients which included persons with disabilities and family members, providers, NWD partner agency staff, and leadership. | The NWD CLC Subcommittee outlined CLC priorities around sustainability to embedding CLC into policy and protocols. This includes a review and recommendations of outreach, intake, and related policies to enhance CLC at the front door. The NWD CLC subcommittee partner agencies will be receiving up to two trainings per selected agency partners by the end of FY18. Collaboration is underway with the Georgetown University National Center for Cultural Competence to produce front door guiding documents. Focus on the Front door to accessing long-term services and supports will be a subcomponent of the District’s CLC Community of Practice on Cultural and Linguistic Competency in Developmental Disabilities. | # of people reached through NWD Core LTSS Agencies' outreach activities. | NWD stakeholder outreach activities to an estimated 400 people, approximately 1,000 recipients of the NWD newsletter | 100
[6 empty] | # of NWD Core LTSS agencies' outreach activities and resources presented in languages other than English. | 2 | 3
Action #2: Develop mandatory training for front line staff of District No Wrong Door partner agencies about the key plans and practice changes being developed through NWD. | Finalize NWD Person-Centered Practices Training for Core NWD LTSS agencies. (NWD) | Ongoing. The NWD Person-Centered Counseling Training is offered twice monthly to all core LTSS front line staff—including an overview of proposed practice changes being developed through NWD. | Ongoing. The NWD Person-Centered Counseling Training is offered twice monthly to all core LTSS front line staff—including an overview of proposed practice changes being developed through NWD. This quarter offering continuing education units for nurses and social workers. The NWD team will continue to work with national experts and core partners to create supplemental learning content for agency staff per job function. | Ongoing. The NWD Person-Centered Counseling Training was offered twice monthly to all core LTSS front line staff—including an overview of proposed practice changes being developed through NWD. NWD project team has worked with the certified nurse trainer to customize the training to RNs and LPNs and establish training calendar for nurses in FY18. The NWD team will continue to work with national experts and core partners to create supplemental learning content for agency staff per job function. | Completed. Monthly NWD person-centered thinking training, continued in Q4 which included key plans and practice changes being developed through NWD. The final customized RN and LPN person-centered practice training includes the NWD key plans and practice changes in development. | # of NWD Training sessions receiving positive participant rating | 12 out of 13 respondents reported a positive experience in Q4 | Baseline
Action #3: Develop a unified messaging and marketing “look” for outreach materials and replicate on all No Wrong Door partner agencies’ websites | Create NWD unified marketing and branding materials for distribution. (NWD) | In collaboration with branding and marketing consultant, LTSS inter-agency staff and community stakeholders, a final version of the logo and renaming has been approved by the NWD Leadership Council. | The renaming of the District's No Wrong Door is DC Support Link: Connections to Support and Services. In collaboration with agency partners, PIOs, and marketing consultant an internal agency marketing plan has been developed. Design concepts and marketing materials will also be developed as well as customer facing webpages. | The renaming of the District's No Wrong Door is DC Support Link: Connections to Support and Services was launched internally across our NWD partner agencies on 9/25/17 at the DC Front Door Summit held at Gallaudet University. Approximately 73 front door staff were in attendance and received marketing tools to better understand, communicate, and promote the NWD system through DC Support Link. They also gained knowledge on national best practices on Person/Family-Centered practices and Cultural and Linguistic Competence to enhance the front door experience for people in need of long-term services and supports. | Completed. The renaming and logo of the District’s No Wrong Door as DC Support Link internally launched at DC Front Door Summit. Externally, the No Wrong Door brand will be publicized via the NWD resource portal to be launched publicly September 2018. In addition, the NWD web page is going through a revamp that will be linked to NWD agency partner’s websites. | # of website hits per month | As we are still developing the design there is no data to measure yet | Baseline
Priority Area #3: Employment
Action #2: Increase the capacity of staff across the Rehabilitation Services Administrations (RSA) through on-site training to support best practices. | Identify and develop core vocational rehabilitation curriculum training for RSA vocational rehabilitation (VR) staff to increase capacity to provide Person-Centered Training on an on-going basis. Provide regular, mandatory training for RSA vocational rehabilitation staff based on policies, procedures, protocols, best practices, and trends identified by the agency. (RSA) | VR staff completed 2 of the 6 modules - Module #1: Introduction to Person Centered Planning; and Module #2: Community Membership: Opportunities for Meaningful Interaction. Part one of each course is offered on-line followed by an on-site discussion/reinforcement session. | VR staff completed 3 of the 6 modules. RSA no longer has a dedicated trainer so the remaining modules will be presented primarily as on-line sessions. A combined presentation has been created and we will continue training using a blended approach utilizing online modules and training from DDS Human Resource trainers. | RSA has completed training for the two day PCT series for all available staff members. RSA has held 5 different training dates, two of which were in August, that facilitated getting all staff trained. The two day series is the Introductory session and an overview of the tools. RSA will continue to train staff, but will do so through the HR department as RSA no longer has a dedicated trainer. Future sessions will be a hybrid of online sessions and in-person sessions. | RSA has continued to enhance trainings and opportunities for growth using the PCT model. In addition to having all RSA staff members complete the two-day PCT training, several supervisors and leaders of RSA participated in Person-Centered Organization Training which helps support the implementation of PCT. Additionally, every Unit in RSA will be completing Unit profiles and a Donut (PCT Tool for Tasks and Responsibilities) to present to the rest of the organization. The aim is to ensure that all individuals are well versed on their responsibilities and the use of PCT tools. | # of Person-Centered Training courses completed by VR staff | 3 of 6 modules (50%) | 33% of PCT Modules
• # of people jointly served by RSA, DDA, DBH, DOES, DCPS.
[6 empty] | • #/% of working-age people with disabilities in competitive, integrated employment. |  | 96%
• # of new, customized employment opportunities created with District support.
• #/% of people with intellectual and developmental disabilities (IDD) supported by RSA to enroll in post-secondary educational programs to reach employment goals of their choice.
Action #3: Increase the number of people with intellectual disabilities (IDD) and serious mental health diagnosis or serious emotional disturbance (SED) who obtain and maintain employment through better coordination of supported employment services with the Developmental Disabilities Administration (DDA) and the Department of Behavioral Health. (WIOA 1.5) | Increase the number of VR Specialists to work specifically with people referred from DDA Supported Employment Services to ensure VR Specialist to Client ratio of 1:150 is maintained. (RSA) | RSA has designated Supported Employment Unit with 3 counselors to serve consumers with IDD and 3 counselors to serve consumers with serious and persistent mental illness. RSA works collaboratively with DDA and DBH to ensure seamless referral system and coordinated service delivery by assigning evidence- based supported employment (EBSE) counselors to EBSE sites where they meet with consumers and treatment teams and having regular monthly meetings between DDA, RSA AND DBH counselors/supervisor to address case management issues pertaining to mutual consumers. | RSA has designated Supported Employment Unit with 3 counselors to serve consumers with IDD. Number of active IDD consumers served is 279, with average caseload size per counselor at 70. Three VR counselors serve consumers with serious and persistent mental illness, a total of 474 and caseload size of average of 119 per counselor. RSA works collaboratively with DDA and DBH to ensure seamless referral system and coordinated service delivery by assigning evidence- based supported employment (EBSE) counselors to EBSE sites where they meet with consumers and treatment teams and having regular monthly meetings between DDA team and RSA counselors/supervisor to address case management issues pertaining to mutual RSA/DDA consumers. | RSA has designated Supported Employment Unit with 3 counselors to serve consumers with serious and persistent mental illness. There are a total of 493 active consumers with a classification of serious and persistent mental illness and the counselor's caseload size is an average of 123 consumers per counselor. RSA works collaboratively with Department of Behavioral Health (DBH) to ensure seamless referral system and coordinated service delivery by assigning evidence- based supported employment (EBSE) counselors to EBSE sites where they meet with consumers and treatment teams. | RSA has designated Supported Employment Unit with 3 counselors to serve consumers with serious and persistent mental illness. There are a total of 482 active consumers with a classification of serious and persistent mental illness and the counselor's caseload size is an average of 160 consumers per counselor. RSA works collaboratively with Department of Behavioral Health (DBH) to ensure seamless referral system and coordinated service delivery by assigning evidence- based supported employment (EBSE) counselors to EBSE sites where they meet with consumers and treatment teams. | # of people with serious mental health impairments (MHI) whose case is closed successfully after obtaining competitive integrated employment. | 119 of 482 YTD Active EBSE Consumers | 100
|  | Supported employment services (including job coaching) are provided to help consumers stabilize and succeed in their employment. Long-term employment supports through waiver services are coordinated and put in place by RSA/DDA team. | Supported employment services (including job coaching) are provided to help consumers stabilize and succeed in their employment. Long-term employment supports through waiver services are coordinated and put in place by RSA/DDA team. | RSA has designated Supported Employment Unit with 3 counselors to serve consumers with IDD. The number of active IDD consumers served is 297, with average caseload size per counselor at 74. RSA works collaboratively with DDA to ensure seamless referral system and coordinated service delivery by assigning evidence- based supported employment (EBSE) counselors to EBSE sites where they meet with consumers and treatment teams. Regular monthly meetings between DDA team and RSA counselors/supervisor to address case management issues pertaining to mutual RSA/DDA consumers and also scheduled to monitor the work. | RSA has designated Supported Employment Unit with 3 counselors to serve consumers with IDD. The number of active IDD consumers served is 298, with average caseload size per counselor at 99. RSA works collaboratively with DDA to ensure seamless referral system and coordinated service delivery by assigning evidence- based supported employment (EBSE) counselors to EBSE sites where they meet with consumers and treatment teams. Regular monthly meetings between DDA team and RSA counselors/supervisor to address case management issues pertaining to mutual RSA/DDA consumers and also scheduled to monitor the work. | # of people with DD/IDD whose case is closed as successful after obtaining competitive integrated employment. | 41 of 298 YTD Active DD/IDD clients | 50
Action #4: Increase the number of people with intellectual disabilities (IDD) and mental health impairments (MHI) who complete training programs that prepare them for jobs in high demand fields, increasing the number of employment placements in these fields. | Obtain baseline data regarding performance outcomes for all current hospitality, health care, IT, construction and security training providers with which RSA has agreements in order to increase the number of effective training providers with agreements. (RSA) | RSA is working closely with DDA to increase referrals for consumers with IDD by having a seamless referral protocol and with training providers to increase training and education programs which maximizes employment opportunities. | Monthly referral protocol meetings between RSA AND DDA have increased to focus on individual client needs and ease of referral navigation. | RSA and DDA continue to host regular meetings to ensure clients receive meaningful support from DDS. The coordinated meetings aim to ensure awareness of employment activities alongside on-going support for quality of life. Recently, RSA and DDA have begun conversations regarding a streamlined approach for intake so that all clients are connected to all services, regardless of which administration the meet with first. | RSA and DDA have developed a streamlined approach to ensuring that individuals receiving services from DDA are able to connect with RSA seamlessly to receive support for employment. Following the DDS realignment, there is now one front door for intake and clients of DDA now no longer have to go through a separate intake process with RSA to receive supports and services. | # of people of working age supported by DDA who received employment services from RSA. | 411 people supported by DDA are receiving services from RSA | 200
|  | RSA works to ensure all RSA consumers regardless of disabilities are assisted with finding and maintaining competitive and integrated employment which pays at least a minimum wage as per the requirements of the local labor laws. Further, collaboration with DBH and its EBSE service providers provides for customized wrap-around services and long-term employment supports for consumers with serious and persistent mental illness. RSA supervisors are closely monitoring employment to ensure it matches consumer's training and education level within the confines of informed choice, and knowledge of career options. Career advancement is an option for consumers under WIOA. | RSA supervisors continue to closely monitoring employment to ensure it matches consumers' training and education level within the confines of informed choice, and knowledge of career options. Career advancement is an option for consumers under WIOA. | RSA continues to ensure that all clients are supported through the agencies that can provide them with the most support to ensure a high quality of life. RSA partners with the Department of Behavioral Health (DBH) to support clients with mental health needs as they seek employment opportunities. RSA has three counselors who co-locate with DBH to ensure we are connecting individuals to the correct services. | RSA continues to ensure that all clients are supported through the agencies that can provide them with the most support to ensure a high quality of life. RSA partners with the Department of Behavioral Health (DBH) to support clients with mental health needs as they seek employment opportunities. RSA has three counselors who co-locate with DBH to ensure we are connecting individuals to the correct services. Currently, 482 clients are receiving supports from both RSA and DBH. This number fluctuates depending on the number of active cases. | # of people supported By DBH who received employment services RSA. | There are 601 clients YTD who were/are connected with RSA and also connected with DBH. | 500
|  | RSA is working with training partners or providers to increase post-secondary and training opportunities for consumers with IDD. | RSA is working with training partners and providers to increase post-secondary and training opportunities for consumers with IDD. | RSA is working to ensure all consumers are connected to employment in a field of their interest and works to align it with several high demand fields. RSA is currently developing programming through connections with our partners to increase postsecondary training opportunities for consumers with IDD. | RSA did not fund any educational or training programs tailored to people with intellectual disabilities in FY17 or FY18. Supported employment sometimes is referred to as the “place and train” model: The client is placed on the job and then training is provided, either by a job coach, manager, co-workers or a combination of on-the-job supports. DDS remains committed to identifying training programs for high demand careers, but recognizes one of the primary challenges exists with access to said training programs for individuals that may not have a diploma. | # increase number of people with intellectual and development disabilities (IDD) supported by RSA who complete post-secondary training programs in high demand industries. | 0 have been enrolled YTD | Baseline
|  | RSA provides training opportunities for all consumers regardless of disabilities--in this vein, consumers with mental illness(es) are in training programs that are consistent with their potentials and preferences. | RSA provides training opportunities for all consumers regardless of disabilities--in this vein, consumers with mental illness(es) are in training programs that are consistent with their potentials and preferences. | RSA has also prioritized work to support our clients with Mental Health diagnosis in connecting them with training for high demand industries. This continues to be an area the RSA is working to enhance programming in over the next quarter. | RSA has also prioritized work to support our clients with Mental Health diagnosis in connecting them with training for high demand industries. RSA has been working with the supported employment team to identify trainings that meet the high demand need and are also meeting the clients interest. Often clients pursue fields that may not be considered high demand fields for employment. | % increase in the number of people with mental health diagnoses supported by RSA who complete post-secondary training programs in high demand industries. | 13 were enrolled YTD | Baseline
Priority Area #5: Intake, Enrollment and Discharge Processes
Priority Area #6: Medicaid Waiver Management and Systems issues
Action #1: Develop the individual and Family supports Medicaid waiver program for people with IDD who live in family homes, including services targeted to help families continue their support. (By December 2017) | Review pre-existing service definitions (and the feasibility of adding new services) in preparation for the HCBS waiver renewal. (DDA) | During the first quarter, DDA Waiver staff approved applications in 3-5 business days. Using this quarter 1 data as a benchmark, Waiver staff will continue to monitor all processes to ensure timely approval of applications, and address systemic issues impacting the approval process as necessary. | The Waiver unit processed waiver enrollment application within 3 business days during April – June. There were 26 persons enrolled into the HCBS IDD waiver during this time period. | DDS/DHCF submitted the final Waiver application to CMS on August 15,2017. Since the submission, CMS has requested additional information on various sections of the proposed Waiver. DDS is working collaboratively with DHCF (and other agencies) to address the questions raised by CMS and will submit responses in October 2017. | The Waiver unit processed waiver enrollment applications within 3 business days during October – December. There were 28 persons enrolled into the HCBS IDD waiver during this time period. | • Decrease average days waiver application processes for those enrolling in waiver services in DDA. | The Waiver unit processed waiver enrollment applications within 3 business days during October – December. There were 28 persons enrolled into the HCBS IDD waiver during this time period. | Decrease from baseline
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
| Review agency and provider performance data from Provider Certification Reviews (PCRs), Provider Performance Reviews (PPRs), incident management and health and wellness standards to identify and address deficiencies in the DDA/DDS service delivery system. (DDA) | The Provider Certification Review (PCR) is conducted to determine if a provider is qualified to deliver the Home and Community Based Services (HCBS) waiver service(s) for which it has been enrolled. During quarter 1, the DDA PCR team completed 30 provider reviews and it was determined that at the conclusion of the initial review, 21 providers (70%) met the certification requirements. The PCR team plans to follow all applicable corrective action procedures with those providers that were unable to certify all services during the initial review. | During quarter 2, the DDA PCR team completed 20 initial/annual provider reviews and it was determined that 16 providers (80%) met the certification requirements. Six follow-up reviews were also completed during this timeframe for those providers who were unable to pass certification during a previous review. 100% of these providers passed the follow-up certification. The PCR team will continue to address those providers that were unable to certify all services during the initial/annual review. | Compared to previous quarters, the Provider Certification Review (PCR) data yielded a compliance percentage signaling a need for a qualitative data review (Q1: 70%; Q2: 80%; Q3: 52%). While the compliance percentage can vary depending on which providers are included in the sample, deficiencies unique to this sample were provided by the PCR team in efforts to identify factors contributing to this decrease. Some of the issues identified include: new providers participating in the PCR for the first time, changes in provider management (and inconsistent record transfer/maintenance) and the inclusion of providers who have inconsistent scorings on the PCR. Quality management staff will continue to review these data and assist providers with all remediation activities to ensure their policies and procedures are in accordance with those of DDS. Staff will also continue to monitor all performance data on a routine basis and implement the necessary follow-up activities with providers and agency staff. | For those that have facility-based day habilitation services beginning in Q4, three are receiving these services above the identified threshold (more than 30 hours); taking the total for CY2017 to 34. Since most authorizations within service plans are active for an entire year, changes in the amount of authorized hours will be analyzed to monitor differences beginning in Q1 of CY2018. | • % of waiver providers that pass certification on the initial provider certification review (PCR) | 13 out of 25 providers (52%) met qualifications for certification during the initial PCR. | 75%
|  | Service authorization data were reviewed for a random sample of people with ISPs effective during quarter 1. For all approved services, 96% of people were receiving at least one service on the same day as the ISP effective date. Consumer records will be reviewed to determine causes for services authorized after the ISP effective date. | For quarter 2, 97% of people were receiving at least one service on the same day as the ISP effective date. For cases where there were services starting after the ISP effective date, this was due to ISP amendments resulting from changes in service needs and/or providers. |  |  | • % of people who (timely) receive the services for which they have been approved/authorized. | 97% 162/167 | 75%
|  | Data review for quarter 1 pending. Updates for Q1 will be provided within the Q2 Olmstead submission. | Service Authorization data (for services starting January 1st - June 30th) were reviewed for providers offering Day Habilitation services in facility based settings as identified by PCR. For all people receiving these services, while the most common frequency is 30 hours a week, 8% (N=26)are receiving services above this threshold. It should be noted that while the number of people receiving services can be reported quarterly, meaningful differences in service hour allocations are best measured at the beginning of each ISP year (annually). Also, the frequency should be revised to review number of hours per week instead of days per week as service needs can allow for a certain number of hours be utilized each day. |  |  | • % decrease in number of people receiving supports from DDA in facility-based programs (for those spending more than 30 hours per week in a day facility).* REFLECTS RECOMMENDED CHANGE | For those that have facility-based day habilitation services beginning in Q4, three are receiving these services above the identified threshold. | 5%
Priority Area #8: Supporting Children and Youth
Action #1: Develop an inter-agency plan to ensure that students with disabilities who graduate with a certificate (rather than a diploma), have at least one community-based, integrated paid work experience prior to school exit. | Establish a MOA with the D.C. Office of the State Superintendent of Education (OSSE) to identify schools to serve certificate track students and begin to draft MOAs with identified schools. Coordinate with D.C. Public Schools (DCPS) to provide work experiences for students in the D.C. Career Academy and for students participating in DCPS general exploration courses. (RSA) | Both DCPS and DC PCS Cooperative have partnered to provide paid, community based, integrated work experiences to students who are on a certificate track. These opportunities are through DCPS' workforce development work based learning programs and through RSA/Special Education Cooperative's youth internship program. RSA provides the salaries and disability supports to all students. The DCPS programs identify host business sites, while the SpeEd CoOp internship program placements are created and fostered by RSA. SpeED CoOp assists RSA in recruiting students at charter schools. | DDS continues to work on implement creative pre-employment transition services designed to attract more unique participants (as opposed to repeat participants). Our outreach efforts are targeting the schools (non-public and charter) and/or very specific populations (severely disabled, sensory disabilities) in an effort to increase the number of new students who participate in pre-employment transition services. The goal of reaching 75% of all eligible students remains feasible. | As the new school year begins, RSA has continued working closely with the LEAs to implement Pre-Employment Transition Services (Pre-ETS). Last school year, RSA was able to deliver Pre-ETS to 1,657 students throughout the district. This was done through strategic partnerships and supports in the public schools, nonpublic schools, and charter schools. The final, unduplicated count indicated that the majority of students reached were classified as ID/DD, however there has been an effort made to reach more students with various disability classifications. The goal is still 75% as we come into the new school year. | RSA was able to provide pre-employment transition services to at least 1050 students in the fourth quarter. In just the first quarter of the fiscal year, we are nearly halfway to reaching our annual goal of providing services to 2,514 students. RSA is in the process of updating our MOA's and MOU's with District LEA's and OSSE to not only maintain our PreETS progress, but to build capacity to ensure the provision of those services to 14 and 15 year olds beginning in 3rd quarter 2018. | • #/% of students with IEPs or 504 Plans receiving at least one Pre Employment Transition Service each school year | 31% (1050/3352) participated in at least one Pre-Employment Transition Service. | 75%
|  |  | As DDS expands its staff, community partners, and provider network, a significantly greater number of students will be exposed to work based learning experiences overall, and in particular paid work experiences. The bulk of the students this quarter represent one LEA (DCPS). As more LEA's and businesses come on board, the number of students served in these experiences will increase. | DDS will continue to provide paid work experiences to students throughout the District as the concerted effort is to ensure all students with disabilities has at least one paid work experience before graduating high school. DDS has encouraged schools to prioritize transition programming for ID/DD students, as they have the most demonstrated need for paid work experience. DDS ended the fiscal year with 237 students having a paid work experience. As students prepare for programming this year, we expect that number to increase. | During the fourth quarter, 128 students received a community-based, integrated paid work experience. 61 of the 128 students who participated are pursuing a Certificate of IEP Completion and are identified as ID/DD. RSA is working closely with LEA's and providers to ensure that these students are placed in both appropriate work settings (conducive to their interests and abilities) and provided the soft skills training necessary for them to meaningfully engage in their work experience. Work readiness training and trainers are utilized extensively for these students to ensure that they receive maximum benefit from their placements. . | • #/% of students with disabilities that have a community-based, integrated paid work experience | 128 students received a community-based, integrated paid work experience | 50
| Review referrals to identify the amount of the time the processing of cases for children with IDD transitioning from out of state facilities takes. (DDA) | During quarter one, of the 17 applications received for youth transitioning into adult DDA services 16 were approved on-time (94%). The one applicant that wasn't approved on-time was incarcerated during the Intake and Eligibility process. | Staff will continue to process applications timely. | DDS received eight applications for youth transitioning into adult DDA services, and all eight were approved on-time. All applications were processed within 45 calendar days. | DDS received fourteen applications for youth transitioning into adult DDA services and two cases were processed within 48 calendar days. Of the two late cases, sufficient documentation wasn't available to make a determination timely. | • #/% of applications received for youth transitioning into adult DDA services that are approved on-time. | 86% 12/14 | 75%
Priority Area #9: Wellness and Quality of Life
| District-wide | The Department on Disability Services (DDS) has continued to actively participate on the “Inclusive Programming Work Group”. DDS has met with stakeholders, subject matter experts; community based organizations and the Department of Parks and Recreation to continually adjust the “Inclusive Programming for All” training slated for the first pilot Summer 2017. | The Department on Disability Services has adjusted the “Inclusive Programming for All” training in partnership with the Department of Parks and Recreation and the DC Office on Aging. Each agency has the goal of piloting the training with at least one stakeholder group for additional feedback before the close of Summer 2017. | DDS developed a training deck and has shared this for review and feedback by DPR, DCOA, ODR and the DC Person-Centered Thinking Learning Community. | To explore future areas for collaboration to meet this action, DDS invited a representative of DCPL to participate in a day service provider meeting to discuss having an Open House for direct support professionals and other support staff from provider agencies to become familiar with all of the services offered by the library. Attendees of the meeting were afforded the opportunity to volunteer and form a committee to ensure the people we serve are integrated and utilizing all the available services based upon their interests. Additionally, a meeting with DDS Deputy Directors was scheduled to discuss braiding in the rollout of the inclusive programming into other agency initiatives to expand its reach and impact in CY18. | • #/% of inclusive daytime program offerings. | Too early to report this data--In CY18 recommend establishing an interagency method of data collection | Baseline
Action #1: Increase inclusive daytime programming offerings and provide technical assistance and training to improve staff capacity at all agencies that provide community programming.
Action #2: Identify ways to give people with disabilities and older adults in the District of Columbia better access to multiple transportation services, allowing for greater mobility with dignity and independence, and easier integration in the community. | DDOT Will complete the accessDC study which will help identify implementation strategies to improve access to special transportation services to older adults PWD (DDA) | Medical Transportation Management (MTM) reports that an average of 871 people with disabilities use the transportation services for which they are eligible. The types of transportation services used includes vans (ambulatory, stretcher and wheelchair), buses, Metro Access and Metrorail. DDA staff will review usage data to further understand all modes of transportation accessed by those that are eligible to receive transportation services. | Medical Transportation Management (MTM) reports that for the month of May 880 people utilized transportation services which include (vans, buses, and Metro) DDA staff will continue to review transportation usage data as well as service authorization data to gain additional information on the varying modes of transportation used and ensure reporting methods are suitable for this metric. | Medical Transportation Management (MTM) reports that for the month of December 845 people utilized transportation services which include (vans, buses, and Metro) DDA staff will continue to review transportation usage data as well as service authorization data to gain additional information on the varying modes of transportation used and ensure reporting methods are suitable for this metric. |  | # of people with disabilities using at least 2 transportation services for which they are eligible. | 880 | Baseline
Note on H13: Price, Emily (DDS): We would like to collect baseline data
Note on I13: Price, Emily (DDS): We would like to collect baseline data
Note on I14: Price, Emily (DDS): We would like to collect baseline