## Olmstead Report CY19 Q2
Quarterly Olmstead Community Integration Summary
CY19 Quarter: | 2
Agency: | DHCF
Due Date: | 2019-07-31
Agency Director: | Wayne Turnage
Olmstead Plan Coordinator: | Leyla Sarigol
CY 19 Quantitative Transition Goal: | TBD (2018 Goal: 30 transitions from institutional settings to HCBS)
Transitions during CY19 Q2 | 10
YTD Transitions: | 18
% of CY19 Quantitative Transition Goal Achieved: | TBD
Detail: | Ten (10) unique enrollments in and/or claims for Personal Care Aide Services, Skilled Nursing, or Adult Day Health Program under the Medicaid State Plan and/or Elderly and persons with Physical Disabilities Home and Community-Based Services Waiver Program within 60 days of discharge for those Medicaid beneficiaries who were discharged from a nursing facility or hospital, April through June, 2019, after a 90+ day stay.
Priority Area: | Year 2 Goal (Included when part of published Olmstead Plan as of 4/30/18; Year 3 Goals TBD) | Narrative: Quarter 2 | Suggested Metrics: | Outcome: | Target
Priority Area #1: A Person-Centered Culture
Action #1: Develop and Implement Person-Centered Policies Across All NWD Core LTSS Agencies. | Develop and recommend clear expectations and competency criteria standards for intake staff consistent with use of person-centered approaches (NWD) | See DDS Report for NWD updates | • #/% of core LTSS agencies that have implemented person-centered service protocols. | 2 of 5 agencies, 3rd agency currently in development | 1
|  |  | # of NWD Core LTSS intake staff that have completed person-centered training. | 41 of the 63 people who attended the PCT course this quarter identified as "front line intake staff." | Baseline
Action Step #2: Add person-centered practice standards to service planning personnel’s employee performance goals in all NWD Core LTSS agencies. | Develop a model of person-centered practice standards and goals that can be incorporated into employee performance measures. (NWD) |  | % of NWD LTSS Core Agencies’ employee performance measures linked to person-centered practices | As we are still developing a method to uniformly collect this data-there is no data to measure yet | 75
|  |  | % of HCBS providers employee performance measures linked to person-centered practices | We recommend removing this metric as this data is not currently being collected by providers. | 75
Action #3: Develop procedures and protocols for supporting family members and others in a person’s support network to ensure that plans accurately and continuously reflect the individual’s preferences and needs. (NWD) | Develop Person Centered Planning Implementation Guidance’ in partnership with stakeholders identifying best practices for supporting families in person-centered planning for NWD Core LTSS agencies and providers. (NWD)
Priority Area #2: Community Engagement, Outreach and Training
2. Community Engagement, Outreach and Training
Action #1: Develop and disseminate policy and protocols to increase linguistically and culturally diverse stakeholder involvement in the development, implementation and ongoing evaluation of NWD core LTSS agencies' engagement and outreach activities | Develop and finalize an assessment of linguistic and cultural competence for NWD Core LTSS agencies intake processes. (NWD) | See DDS Report for NWD updates | # of people reached through NWD Core LTSS Agencies' outreach activities. | NWD stakeholder outreach activities to an estimated 400 people, approximately 1,000 recipients of the NWD newsletter | 100
|  |  | # of NWD Core LTSS agencies' outreach activities and resources presented in languages other than English. | 2 | 3
Action #2: Develop mandatory training for front line staff of District No Wrong Door partner agencies about the key plans and practice changes being developed through NWD. | Finalize NWD Person-Centered Practices Training for Core NWD LTSS agencies. (NWD) |  | # of NWD Training sessions receiving positive participant rating | 42 out of 43 respondents reported a positive experience | Baseline
Action #3: Develop a unified messaging and marketing “look” for outreach materials and replicate on all No Wrong Door partner agencies’ websites | Create NWD unified marketing and branding materials for distribution. (NWD) |  | # of website hits per month | As we are still developing the design there is no data to measure yet | Baseline
Priority Area #3: Employment
Action #2: Increase the capacity of staff across the Rehabilitation Services Administrations (RSA) through on-site training to support best practices. | Identify and develop core vocational rehabilitation curriculum training for RSA vocational rehabilitation (VR) staff to increase capacity to provide Person-Centered Training on an on-going basis. Provide regular, mandatory training for RSA vocational rehabilitation staff based on policies, procedures, protocols, best practices, and trends identified by the agency. (RSA) | See DDS Report | # of Person-Centered Training courses completed by VR staff | 3 of 6 modules (50%) | 33% of PCT Modules
• # of people jointly served by RSA, DDA, DBH, DOES, DCPS.
|  |  | • #/% of working-age people with disabilities in competitive, integrated employment. |  | 96%
• # of new, customized employment opportunities created with District support.
• #/% of people with intellectual and developmental disabilities (IDD) supported by RSA to enroll in post-secondary educational programs to reach employment goals of their choice.
Action #3: Increase the number of people with intellectual disabilities (IDD) and serious mental health diagnosis or serious emotional disturbance (SED) who obtain and maintain employment through better coordination of supported employment services with the Developmental Disabilities Administration (DDA) and the Department of Behavioral Health. (WIOA 1.5) | Increase the number of VR Specialists to work specifically with people referred from DDA Supported Employment Services to ensure VR Specialist to Client ratio of 1:150 is maintained. (RSA) | See DDS Report | # of people with serious mental health impairments (MHI) whose case is closed successfully after obtaining competitive integrated employment. | 95 of 474 YTD Active EBSE Consumers | 100
|  |  | # of people with DD/IDD whose case is closed as successful after obtaining competitive integrated employment. | Number of mutual active RSA/DDA consumers is 362 to date. Number of IDD consumers who obtained employment is 3 for the 1st quarter and 4 during the 2nd quarter. | 50
Action #4: Increase the number of people with intellectual disabilities (IDD) and mental health impairments (MHI) who complete training programs that prepare them for jobs in high demand fields, increasing the number of employment placements in these fields. | Obtain baseline data regarding performance outcomes for all current hospitality, health care, IT, construction and security training providers with which RSA has agreements in order to increase the number of effective training providers with agreements. (RSA) | See DDS Report | # of people of working age supported by DDA who received employment services from RSA. | A total of 299 DDA consumers were receiving RSA services in the first quarter and 362 in the second quarter. | 200
|  |  | # of people supported By DBH who received employment services RSA. | There were 497 consumers supported By DBH who received employment services from RSA in the first quarter and 474 in second quarter. | 500
|  |  | # increase number of people with intellectual and development disabilities (IDD) supported by RSA who complete post-secondary training programs in high demand industries. | Developing Methodology to Quantify. | Baseline
|  |  | % increase in the number of people with mental health diagnoses supported by RSA who complete post-secondary training programs in high demand industries. | 10 were enrolled YTD | Baseline
Priority Area #4: Housing
Latest EPD Waiver renewal and regulatory amendment included an increase in the Assisted Living Facility reimbursement rate from $60 daily to $155 daily. This was intended, in part, to increase the incentive for Assisted Living providers to participate in DC's Medicaid program, thereby increasing the continuum of affordable and accessible housing options available to residents with LTC needs. Progress continues with the development of a 150-unit assisted living facility East of the River. It is slated for a 2020 opening. Last quarter, DHCF participated in a forum to identify similar opportunities for collaboration in the District that was convened by DC Health and partners on this project. DHCF looks forward to continued participation in the Housing Work Group of the Age-Friendly Task Force. One objective for particpating is to increase housing opportunities for extremely low-income (at or below 30% AMI) people who represent many of the families that Medicaid serves. During the quarter, DHCF expressed interest to the DC Housing Authority in re-opening enrollment for the Marigold assisted living facility, one of the District's 3 ALF's currently enrolled in Medicaid. DHCF's request followed DC Health's decision to lift a sanction that had been placed on the facility. As of this report, DCHA does not plan to re-open enrollment.
During the quarter, with Money Follows the Person Demonstration activities focusing on sustainability, maintenance of the Long Term Care Housing Choice Vouchers and associated processes continued with the DC Department on Aging and Community Living's Aging and Disability Resource Center, the current operational agency for the selection of individuals for the vouchers, and related application assistance. This period, in conjunction with CMS, DHCF confirmed that the District did not receive an award in response to its 2018 application for Non-Elderly persons with Disabilities (NED) vouchers.
Priority Area #5: Intake, Enrollment and Discharge Processes
Action #1: Develop a "person-centered profile" for use in NWD Core LTSS agencies with common information that can be collected by referral sources or state systems and shared to avoid duplication of effort. | Develop a model person-centered profile for use across NWD Core LTSS agencies. | See DDS Report | % of EPD case managers that participated in training | Approximately 120/150 individuals from provider network (80%). | Baseline
Action #2: Implement an interagency case management system. | Finalize system and train partner agency staff on new system for launch. | The Clinical Case Management System (CCMS), named DC Care Connect, launched in July 16, 2018. DHCF conducted trainings on the new system during the weeks of June 18th and June 25th. The training sessions reached DHCF and sister agency staff (DACL, ESA), Quality Review and Participant-Directed Services contractors, and Medicaid-enrolled Adult Day Health, Home Health Agency and Elderly and persons with Physical Disabilities Home and Community-Based Waiver program providers. DHCF preceded the trainings with a week of User Acceptance Trainingin June 2018 for a sub-group of the audience above to identify and resolve issues ahead of the launch. The new system supports increased monitoring of the implementation of person-centered service plans (PCSPs). The plan itself is more comprhensive in DC Care Connect, and features of the system ensure alignment of the monthly clincal notes with the PCSP. Any incidents experienced are also mapped to the PCSP. Since the launch, DHCF LTCA has been working with the DC Care Connect vendor, sister agencies, and providers to identify needed system improvements and make changes accordingly. To facilitate access to home and community-based services, DHCF expanded DCCC users to include nursing facilities. A training for NFs is planned in August 2019. | % of EPD waiver participants who have service plans that address their personal goals | 96/151 (64%) waiver year to date through March 31, 2019. These figures are current with latest required reporting to CMS for the EPD Waiver, Waiver Year 2, based on waiver renewal application approved April 4, 2017. The report for the period ending July 30, 2018 included annual figure for WY 1 (82%). This report includes the annual figure for WY 2. | 86%
Action #3: Develop guidance and training for case managers and service coordinators to ensure that the plans they create at intake and enrollment reflect a person's preferences and needs, and plans are adjusted as necessary. | For EPD Waiver case managers, continue implementation of quality assurance and monitoring to review the inclusion of personal goals and health and safety risks in service plans. | Monitoring continued during the quarter as indicated in the metrics for this goal. For Waiver Year (WY) 1 that ended March 31, 2018, the annual target for the inclusion of personal goals in service plans was on track at 82 of a desired 86%. For WY 2 ending March 31, 2019, performance decreased to 64% (96/151). 1:1 technical assistance with indentified providers is intended to increase aggregate performance on this measure. The target for the inclusion of health and safety risks in service plans also continues to present an opportunity for education and improvement though improved performance was demonstrated by providers during the quarter relative to WY1 (40% in WY 1, up to 55% for WY 2). The LTCA continues to focus on education and training on the inclusion of health and safety risks in service plans as part of its learning collaborative and monitoring activities. The inclusion of personal goals in service plans will also be incorporated into technical assistance. | % of EPD waiver participants who have service plans that address their health and safety risks | 82/151 (54%) waiver year to date through March 31, 2019. These figures are current with latest required reporting to CMS for the EPD Waiver, Waiver Year 2, based on waiver renewal application approved April 4, 2017. The report for the period ending July 30, 2018 included annual figure for WY 1 (40%). This report includes the annual figure for WY 2. | 80%
Action #4: Increase the number of nursing facility discharges through improvements to the DACL's Community Transition Program. | Shift the focus of DC Department on Aging and Community Living's Housing Coordinator from general housing assistance to primarily assisting Community Transition clients in identifying housing. Broaden the role of community transition staff to include assisting MFP Outreach Coordinator in outreach work to nursing facilities. Draft and publish rule establishing Community Transition Services in the EPD Waiver providing up to $5,000 per person for household set-up and transition expenses for people transitioning from nursing facilities to the community. | On December 1, 2018, DHCF launched the new "Transition" eligibility program code which indicates that a nursing or other LTC facility resident planning for discharge and transition to the community under Medicaid HCBS is eligible for Medicaid EPD Waiver services upon discharge. The planning and implementation represents a collaboaration between DHCF, the Department of Human Services, Economic Security Adminsitration, and the DC Department on Aging and Community Living's Aging and Disability Resource Center. The transition code and associated processes allow for identified EPD Waiver services, e.g. Community Transition Services-Household Set-Up, and Case Management, to be authorized and delivered before discharge from the LTC facility. It also allows the prior authoriztaion of Personal Care Services at the full level of care before discharge from the LTC facility. This ensures continuty of needed personal care assistance with activities of daily living that begins at home on the day of discharge. The eligibility determination before discharge from the facility has facilitated the acceptance of these residents by Home Health Agencies (HHAs) for services. DHCF continued work with partner agencies to implement and refine the process during the period. | # of clients transitioned into the community with the help of DACL's Community Transition Program | (See DACL ADRC data) | 45
Priority Area #6: Medicaid Waiver Management and Systems issues
Action #1: Develop the individual and Family supports Medicaid waiver program for people with IDD who live in family homes, including services targeted to help families continue their support. (By December 2017) | Review pre-existing service definitions (and the feasibility of adding new services) in preparation for the HCBS waiver renewal. (DDA) |  | • Decrease average days waiver application processes for those enrolling in waiver services in DDA. | Compared to quarter 1, there has been a decline in the time taken to approve waiver applications. With approvals occurring in a short timeframe, the 15% decrease poses a negligible difference (less than 1 day for a 5 day approval). However, efforts will continue to ensure this downward trend remains consistent. | Decrease from baseline
Action #2: Conduct training on how to access Medicaid Waiver services and troubleshoot during enrollment for agency, providers, DACL lead agency, LTC facility, and hospital staff involved in the EPD Waiver process |  | • EPDW/State Plan provider meetings were convened in April, June and July 2019. Learning Collaboratives have been incorporated into the meeting format, providing an opportunity to showcase promising practices in the provider network and to exchange information in small groups of HCBS providers and DHCF agency staff. The June meeting focused on person-centered service planning and care coordination. The July meeting highlighted access to Medicaid benefits and community resources. • LTCA staff continue to participate in the Long Term Care Coalition meetings held on the second Wednesday of the month to engage with stakeholders, provide updates and respond to any concerns or issues raised. • LTCA, in collaboration with the ADRC, will convene a summit/training for nursing facilities in August 2019. Among other topics, access to home and community-based services for residents who want to transition back to the community will be covered. | Average EPD and IDD Waiver endollment times (See DACL DACL and DDS data, respectively) | (See DACL ADRC and DDS data, respectively)
Action #3: Assure quality in the newly implemented Participant Directed Services Program, allowing people receiving EPD Waiver services to have responsibilty for managing and directing all aspects of service delivery, including who provides the services and how the services are provided |  | The PDS program known as Services My Way continues to see tremendous growth and currently has over 750 active participants. DHCF monitors quality of services by consistently reviewing our VF/EA Financial Management Services-Support Broker contractor. DHCF completed the annual performance audit for the VF/EA FMS- Support Broker contractor on December 13th and 14th , 2018. DHCF continues to train case management agencies on the PDS program, which is intended to educate and increase quality of the services being delivered. The VF/EA FMS-Support Broker contractor also completes annual satisfaction surveys. DHCF continued to engage stakeholders through bi-monthly meetings to seek feedback on beneficiaries' experiences. This quarter, a SMW stakeholder meeting was convened July 26, 2019. | # of public events/participants on LTSS system access and Medicaid Waiver protocols and processes | (See DACL ADRC data)
Action #4: Implement complaint tracking and management system for the EPD Waiver Program. |  | During CY19 Q2, 1) DHCF continues to monitor reporting trends and milestones (Via DCCC Incident Reporting Tools) and provide ongoing training and best practice guidelines to improve Providers’ incident reporting capability. Ongoing-Weekly Provider Incident Report Management Dashboards which provide reminders to Providers on outstanding Incident Reports, Investigations and incidents Pending Implementation of corrective/mitigating action plans. 2)DHCF shared and reviewed CMS guidance on Incident management for HCBS with Providers during a Learning Collaborative session on Incident Management held on 5/23/2019. 3) Individual and aggregate Provider Score cards were developed and shared with EPD Waiver and State Plan Providers during the Learning Collaborative session on Incident Management. Scorecards, performance improvement strategies and best practices were shared with Providers at the learning Collaborative with EPDW 5/23/2019. Providers can view daily or weekly performance scorecards upon request. a.Incident Report Scorecards are disseminated to providers on a quarterly basis. b.Areas for improvement are discussed with Providers (individually) on an ongoing basis-Providers who consistently fail to meet the required standards on reporting are being notified and requested to attend mandatory TA sessions with their Incident Report Admin and designated staff required to attend. 4) DHCF initiated discussions with DACL in preparation for the transfer of the Adult Protective Services Unit from DHS to DACL by October 2019. 5) DHCF is currently exploring ways to get all of the appropriate stakeholders at the table: a.Create a Steering (Larger) Group i.e. APS, Behavioral Health, AGs Office- MFCU b. Several smaller work groups- Ongoing discussions with identifying other stakeholders on Incident Management across the District- Meeting schedule will proceed post-APS relocation to DACL. | % of EPD Waiver complaints investigated within 7 days | 1,120/1,175 (95%) waiver year to date through March 31, 2019. These figures are current with latest required reporting to CMS for the EPD Waiver, Waiver Year 2, based on waiver renewal application approved April 4, 2017. The report for the period ending July 30, 2018 included annual figure for WY 1 (90%). This report includes the annual figure for WY 2. | 80%
|  |  | % of beneficiaries’ critical incidents where appropriate follow-up was implemented within 30 days of closure of investigation | 34/67 (51%) waiver year to date through March 31, 2019. These figures are current with latest required reporting to CMS for the EPD Waiver, Waiver Year 2, based on waiver renewal application approved April 4, 2017. The report for the period ending July 30, 2018 included annual figure for WY 1 (87%). This report includes the annual figure for WY 2. | 50%
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
Action #1: Reduce the number of nursing facility admissions by increasing accessbility to community-based services. | Improve tracking mechanisms for DACL's Options Counseling servie and establish a baseline for number of people served through DACL's Options Counseling. | See DACL narrative and data | # of people receiving options counseling through DACL | (See DACL ADRC data) | Baseline
Action #2: Assess and reduce duplication of service offered by Medicaid and DACL. | Reduce duplication by tracking Case Management across DC funding sources; assisting DACL grantees in becoming EPD Waiver providers; and establishing procedures to ensure against duplication for clients transitioning from one DC Case Management funding source to another. | DHCF and DACL continue to coordinate relative to case management services. With the launch of a new EPD case management system in July 2018, the focus on person-centered planning was strengthened. In addition, agency and staff assignments are clearly identified across govermental and Medicaid-enrolled agencies. Three DACL grantees/senior lead agencies enrolled EPD Waiver providers at the close of CY19 Q1. Two are enrolled as case management providers, and the third is an Adult Day Health Program provider. | # of DHCF and DACL case management trainings completed collaboratively by both agencies annually | Data pending | Baseline
Action #3: Review and strengthen regulatory options to more effectively deal with quality issues when they arise | Review agency and provider performance data from Provider Certification Reviews (PCRs), Provider Performance Reviews (PPRs), incident management and health and wellness standards to identify and addess deficiencies in the DDA/DDS service delivery system | See DDS narrative and data | # of Medicaid beneficiaries using EPD Waiver Services who also received assistance through DACL's Senior Services Network | Data pending | Baseline
Action #4: Review all providers' Language Access plans to ensure residents with limited English proficiency have access to linguistically and culturally appropriate services. | Update all provider review tools by adding questions specifically addressing compliance with DHCF's Language Access plan and policies. | Since CY 2017, DHCF delivered trainings to 716 staff representing 364 enrolled DC Medicaid providers. | # of people enrolled in the 1915 (i) and EPD Waiver Adult Day Health Program | 172 | Baseline
Action #5: Create a customer satisfaction survey to cover the five components of quality described above. |  | LTCA developed and administered an EPD Waiver Beneficiary Satisfaction Survey for the first phase of the provider report card. Its results were the basis for the first report card published in CY18 Q4 (see additional details below). | % of new provider applications, by type, who met EPD Waiver provider readiness | 4/4 (100%) waiver year to date through March 31, 2019 (no change since last quarter). These figures are current with latest required reporting to CMS for the EPD Waiver, Waiver Year 2, based on waiver renewal application approved April 4, 2017. The report for the period ending July 30, 2018 included annual figure for WY 1 (100%). This report includes the annual figure for WY 2. | 95%
Action #6: Strengthen assurance of EPD Waiver provider standards from provider enrollment to monitoring, and at three-year recertification |  | LTCA, in collaboration with its Quality Division, established quality assurance measures consistent with the EPD Waiver Renewal effective April 4, 2017. The quality measures address each assurance area under the 1915 (c ) waiver authority, including qualified providers. Sub-assurances and measures collected quarterly address data at provider enrollment, and on-going through monitoring. (see outcomes of monitoring in Metrics.) At the end of the first Waiver Year on March 31, 2018, areas for improvement include inclusion of health and safety risks in services plans, and ensuring that participants receive services at the level they are needed. At the close of Waiver Year 2, the inclusion of personal goals in service plans had also emerged as an area for education and improvement. These areas continue to be the focus of training and education with EPD Waiver providers in CY19. | % of EPD Waiver beneficiaries selecting new provider agencies who use the provider report card to inform selection | Data will be available beginning in CY2019 | Baseline
Action #7: Develop and publish EPD Waiver provider report card |  | Working with its Quality Division, DHCF launched its EPD Waiver provider report card. The report card is being released in phases. The first phase includes information from EPD Waiver Beneficiary Satisfaction Surveys. Subsequent phases will include LTCA monitoring data. DHCF published the score card for EPD Waiver case management agencies in CY18 Q4. | % of Waiver providers that pass certification on the initial provider certification review (PCR) | (See DDS data) | 75%
|  |  | % of waiver participants who received services specified in the ISP in accordance with the type, scope, amount, frequency and duration specified in the ISP | 105/151 (70%) waiver year to date through March 31, 2019. These figures are current with latest required reporting to CMS for the EPD Waiver, Waiver Year 2, based on waiver renewal application approved April 4, 2017. The report for the period ending July 30, 2018 included annual figure for WY 1 (59%). This report includes the annual figure for WY 2. | 75%
|  |  | % decrease in number of people receiving supports from DDA in facility-based day programs (for those spending 4 or more days per week in a day facility) | (See DDS data) | 5%
Priority Area #8: Supporting Children and Youth
Action #1: Develop an inter-agency plan to ensure that students with disabilities who graduate with a certificate (rather than a diploma), have at least one community-based, integrated paid work experience prior to school exit. | Establish a MOA with the D.C. Office of the State Superintendent of Education (OSSE) to identify schools to serve certificate track students and begin to draft MOAs with identified schools. Coordinate with D.C. Public Schools (DCPS) to provide work experiences for students in the D.C. Career Academy and for students participating in DCPS general exploration courses. (RSA) | See DDS narrative and data
| Review referrals to identify the amount of the time the processing of cases for children with IDD transitioning from out of state facilities takes. (DDA) | See DDS narrative and data
Priority Area #9: Wellness and Quality of Life
| Districtwide |  | • #/% of inclusive daytime program offerings. |  | Baseline
Action #1: Increase inclusive daytime programming offerings and provide technical assistance and training to improve staff capacity at all agencies that provide community programming. |  | See DDS narrative and data
Action #2: Identify ways to give people with disabilities and older adults in the District of Columbia better access to multiple transportation services, allowing for greater mobility with dignity and independence, and easier integration in the community. | DDOT Will complete the accessDC study which will help identify implementation strategies to improve access to special transportation services to older adults PWD (DDA) |  | # of people with disabilities using at least 2 transportation services for which they are eligible. |  | Baseline
See DDS narrative and data
Note on E19: Price, Emily (DDS): We would like to collect baseline data
Note on F19: Price, Emily (DDS): We would like to collect baseline data
Note on F20: Price, Emily (DDS): We would like to collect baseline