## Olmstead Report CY19 Q1
Quarterly Olmstead Community Integration Summary
CY19 Quarter: | 1
Agency: | DDS
Due Date: | 2019-04-30
Agency Director: | Andrew Reese
Olmstead Plan Coordinator: | Ed Bynum
Priority Area: | Year 3 Goal | Narrative: Quarter 1 | Suggested Metrics: | Outcome: | Target | Comments
Priority Area #1: A Person-Centered Culture
Action #1: Develop and Implement Person-Centered Policies Across All NWD Core LTSS Agencies. | Finalize model policies and procedures for all NWD Core LTSS agencies intake staff consistent use of person-centered approaches. | In CY18 it was known that 2 out of 5 core NWD LTSS Agencies intake staff performance measures were linked to person-centered practices. On-going metrics pertaining to policies and procedures for intake staff is an inter-agency measure. | • #/% of core LTSS agencies that have implemented person-centered methodology for intake staff. (to be reviewed) | DDS No-longer the lead; Now Intra-Agency Measure (Metric may be revised) |  |  | Responsible Person - Emily Price
Action 1.2 - Add person-centered practice standards to service planning personnel’s employee performance goals in all NWD Core LTSS agencies. | Develop model person-centered position descriptions for NWD Core LTSS agencies service planning personnel. | Year 3 goal was completed in CY17 (May-June). On-going metrics data is an intra-agency measure. DDS will explore adding a person-centered practice competency for staff in CY20. | % of NWD LTSS Core Agencies employee performance measures linked to person-centered practices. (To be reviewed) | Completed |  |  | Responsible Person - Emily Price
Action #3: Develop procedures and protocols for supporting family members and others in a person’s support network to ensure that plans accurately and continuously reflect the individual’s preferences and needs. (NWD) | Finalize model Supporting Family policy and protocols in partnership with families served in NWD Core LTSS agencies. | DDS assisted the Family Support Council in applying to join the National Resource Center on Supported Decision-Making (SDM) Community of Practice. In Q1 the Family Support Council was accepted into the CoP, and hosted two focus group sessions on SDM. The focus groups targeted model policy, protocols, and associated training related to SDM. The findings and technical assistance provided by the grant, contributed to understanding the model of support families are requesting. | % NWD LTSS Core Agencies' intake performance measures linked to person-centered practices (to be reviewed) | DDS No-longer the lead; Now Intra-Agency Measure (Metric may be revised) |  |  | Responsible Person - Emily Price
Priority Area #2: Community Engagement, Outreach and Training
Action #1: Develop and disseminate policy and protocols to increase linguistically and culturally diverse stakeholder involvement in the development, implementation and ongoing evaluation of NWD core LTSS agencies' engagement and outreach activities | Develop model cultural and linguistic competency policies and procedures, and a cultural and linguistic framework for NWD Core LTSS agencies to support culturally and linguistically competent practices. | In Q1, DDS hosted several monthly outreach activities reaching approximately 1,550 community members--this includes people and family members of people receiving services or supports; transition-aged youth and their families; DCPS secondary special education staff; the Department of Parks and Recreation managerial staff; disability advocates; and community members interested in learning more about persons with disabilities through DD Awareness Month (March) events. Resources were provided in Spanish for 2 events and interpreters for ASL and Mandarin were also provided as requested. During the Voices of Change conference on March 29th the parent session presentations were provided in English and Spanish. | # of people reached through NWD Core LTSS agencies outreach activities | 1550 |  |  | Responsible Person/People - Mark Agosto, Emily Price, Yufani Nshom
|  |  | # of outreach activities and resources presented in languages other than English | 3 | 5 |  | Responsible Person/People - Mark Agosto, Emily Price
Action #2: Develop mandatory training for front line staff of District No Wrong Door partner agencies about the key plans and practice changes being developed through NWD. | Update NWD Person Centered Practices training surveys to better collect participant feedback, and develop a unified survey tracking tool. | Completed. This quarter, the PCT curriculum was updated as well as the post-training survey and summary responses tracking tool. | # of NWD training sessions receiving positive participant rating | Completed |  |  | Responsible Person/People - Emily Price
Action #3: Develop a unified messaging and marketing “look” for outreach materials and replicate on all No Wrong Door partner agencies’ websites | Assess user experience webpage to enhance NWD Webpage utility. | No Wrong Door’s implementation of the DC Support Link Resource Portal has proven to be a resource that people and intake staff have actively visited to access information about services and supports. During the 1st quarter calendar year, from January 1st- March 31, 2019 the website has received: • Intellectual and Developmental Disabilities: 620 Total Hits • Older Adults and People with Disabilities: 396 Total Hits • Behavioral Health: 11595 Total Hits • Veterans: 2303 Total Hits | # of website hits per month | Intellectual and Developmental Disabilities: 620 Total Hits • Older Adults and People with Disabilities: 396 Total Hits • Behavioral Health: 11595 Total Hits • Veterans: 2303 Total Hits | 50 |  | Responsible person - Donald Clark
Priority Area #3: Employment
Action #2: Increase the capacity of staff across the Rehabilitation Services Administrations (RSA) through on-site training to support best practices. | All VR staff will use Person-Centered-Thinking concepts to develop employment goals for persons served by RSA | RSA's leadership, counselors and staff regularly participates in PCT-Training and practices PCT principles and concepts with client engagement via Informed Choice to ensure clients are driving their vocational desires, interests and goals. RSA also ensures PCT in supervisory styles and approaches and applies the PCT tools in the various work Units across teams to ensure RSA remains a PCO. | % of Person-Centered Training courses completed by VR staff | 100% | 100% |  | Responsible person - Taylor Kenny
Action #3: Increase the number of people with intellectual disabilities (IDD) and serious mental health diagnosis or serious emotional disturbance (SED) who obtain and maintain employment through better coordination of supported employment services with the Developmental Disabilities Administration (DDA) and the Department of Behavioral Health. (WIOA 1.5) | Assign three (3) VR counselors to work with all people referred from DBH for evidenced based supported employment services. Increase the number of VR Specialist to work specifically with people referred from DBH to ensure VR Specialist to client ration of 1:150 is maintained. | RSA and Department of Behavioral Health continue to coordinate services for individuals with Mental Health Illnesses via our Evidence Based Supported Employment Unit. The referral process coordinates service delivery through assigning VRC's to sites in which the counselor is able to meet with treatment teams and consumers. the Unit Supervisor additionally regularly meets with the DBH Program Manager to ensure continuity of service delivery occurs seamlessly. | # of people with serious mental health impairments (MHI) whose case is closed successfully after obtaining competitive integrated employment | 24 | 120 |  | Responsible person - Brett Hymas (System 7?)
|  | RSA's Evidenced based/Supported Employment unit has added an additional VRC-newly hired, to provide services to the IDD population, increasing the number from 3 to 4 VRC's affecting change for the individuals we serve. Also, regular monthly meetings occur between the DDA Support Coordination Team and RSA Counselors to review case management concerns to which require a multidisciplinary approach for resolution. Further, Department of Behavioral Health and the EBSE Unit engage in communication and collaboration | # of people with DD/IDD whose case is closed as successful after obtaining competitive integrated employment | 9 | 70 |  | Responsible person - Brett Hymas (System 7?)
Action #4: Increase the number of people with intellectual disabilities (IDD) and mental health impairments (MHI) who complete training programs that prepare them for jobs in high demand fields, increasing the number of employment placements in these fields. | Expand the provision of job readiness training for DCRSA job seekers, by both DCRSA Business Relations Unit (BRU) staff and through contracts with provider agencies. Provide training to counselors to ensure that they are able to use labor market information in assisting people to develop employment goals that are consistent with the person's strengths, needs, resources, abilities, capabilities, and prepares the person for work that is available in high demand fields in the District economy. | RSA Employment Coordinators and the EBSE Employment Coordinator provide Job readiness training, resume building skills, job search understanding and job workshops four days a week in the RSA "Resource Room", pairing training with IPE goals to prepare clients to meet with | # of people of working age supported by DDA who receive employment services from RSA. | 406 | 250 |  | Responsible person - WongDuen Coley
|  | Awaiting Narrative | # of people supported by DBH who receive employment services from RSA | 272 | 550 |  | Responsible person - Brett Hymas
Priority Area #4: Housing
Priority Area #5: Intake, Enrollment and Discharge Processes
Priority Area 6: Medicaid Waiver Management and Systems issues
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
Action 3: Review and strength regulatory options to more effectively deal with quality issues when they arise. | As needed, update policy and procedures and amend applicable regulations to allow for stronger sanctioning of providers. |  | % of waiver providers that pass certification on initial provider certification review (PCR) |  | 85% | Responsible person - Barbara Stachowiak
|  | Data for Q1 of CY19 identified 3 people that received services after the ISP effective date. In all cases, there was a delay in service start dates for supported living services. Case documentation show that these perceived delays in residential placements can be attributed to transitions from respite/natural home placements and identifying providers with capacity to address specific support needs. There were no lapses in residential coverage. Staff will continue to assess service and support needs as documented in the person-centered ISP in efforts to timely identify providers and supports that best align with the needs of each person receiving services from DDA. | % of people who receive the services for which they have been approved/authorized(according to the ISP effective date) | 157/160 = 98% | 85% |  | Responsible person - Charlotte Roberts
|  | With DDS having a mission that focuses on providing services that lead to meaningful opportunities for community inclusion , there has been a change in the way this metric is calculated for Olmstead Year 3. Working to ensure that efforts are targeted towards decreasing the number of people using facility-based only services, DDA is now monitoring the number of people receiving Day Habilitation services in these settings for 24 or more hours a week (opposed to the previous level of 30 hours a week). This tracking allows for staff to identify people that are choosing to remain in facility-based day services (using informed choice procedures), and that opportunities for experiences in other settings are made available according to needs and interests. As in previous Olmstead years, these data will be tracked quarterly and compared annually to calculate the percent decrease. | % decrease in number of people receiving supports from DDA in facility-based day programs (determined by the number of authorized units hours per week - 24 hours/week or more) | CY19- Q1: (N= 160) | 10% |  | Responsible person - Charlotte Roberts
Action 4: Review all providers' Language Access plans to ensure residents with limited English proficiency have access to linguistically and culturally appropriate services. | Review case records for consumers with limited English proficiency to gain insight on what barriers still exist in terms of accessing services.
Priority Area #8: Supporting Children and Youth
Action #1: Develop an inter-agency plan to ensure that students with disabilities who graduate with a certificate (rather than a diploma), have at least one community-based, integrated paid work experience prior to school exit. | Attend pre-exit IEP meetings for all students on certificate track to ensure that appropriate integrated post-secondary activities (i.e. training, education, employment) are identified. | RSA Pre-ETS Services engages Children and Youth with training programs such as Direct Support Professional Academy, Project SEARCH and other general exploration programs. | % of students with IEPs or 504 plans receiving at least one Pre-Employment Transition Service each school year | 39% | 85% |  | Responsible person - Taylor Kenny
|  |  | # of students with disabilities that have a community-based. Integrated paid work experience | 80 students | 100 |  | Responsible person - Taylor Kenny
Action #2: Increase the timely submission and completion of applications for adult DDA services for children with IDD who are out of state residential facilities. | Continue to work with CFSA to identify additional ways DDA can assist in streamlining the transition process. | For this quarter, there are not any number of out-of-state placement DC Students referred. | #/% of applications received for youth transitioning into adult DDA services that are approved on-time (Metric originally reported by DDA, but was only applicable for Olmstead Year 1) | Number of total DC student referrals: 25 |  |  | Responsible Person/People - Mark Agosto, Brenda Davis, Michelle Hawkins
Action 3: Develop NWD Person-Centered Practices curriculum and train Mentor Trainers to deliver the training to NWD Core LTSS agencies and community Partners | Create a PCT section of the NWD webpage that includes PCT resources, including tools and webinars. | The NWD initiative launched the 2.0 version of the Network of Care, “DC Support Link Resource Portal” on September 28, 2018. Upon the launch of the Resource Portal, it made readily available a host of Vision and Person-Centered Planning tools to frontline staff, people with disabilities and their circle of support. The tools enable people to: • Organize information about themselves • Receive Guidance with daily decision making • Develop a vision of a good life • Identify how to find supports • Discover what it takes to live the life they want
Priority Area #9: Wellness and Quality of Life
Action #2: Identify ways to give people with disabilities and older adults in the District of Columbia better access to multiple transportation services, allowing for greater mobility with dignity and independence, and easier integration in the community. | Establish working group of partner agencies to meet regularly and implement short-term recommendations and identify funding for long term recommendations of the accessDC study |  | • #/% of inclusive daytime program offerings. |  | Baseline
|  |  | # of people with disabilities using at least 2 transportation services for which they are eligible. |  |  | Recommend deleting this measure. DDOT (as the main agency responsible) is using their own system for tracking and reporting these transportation data. These metrics do not align with the goal. If we want to keep the metric on inclusive daytime programs offered by DC agencies, we should change the goal and ensure involvement of DCPL and DPR.