## Olmstead Report CY18 Q1
Quarterly Olmstead Community Integration Summary
CY18 Quarter: | 1
Agency: | DDS
Due Date: | 2018-05-16
Agency Director: | Andrew Reese
Olmstead Plan Coordinator: | Ed Bynum
Priority Area: | Year 2 Goal | Narrative: Quarter 1 | Suggested Metrics: | Outcome: | Target | Comments | Existing Goals
Note: We are in Year 2 currently. Items in yellow are recommended changes to NWD goals
Priority Area #1: A Person-Centered Culture
Action #1: Develop and Implement Person-Centered Policies Across All NWD Core LTSS Agencies. | Host community meetings to garner stakeholder feedback on the person-centered policies and procedures for all NWD core LTSS agencies' intake staff. | The No Wrong Door project team facilitates monthly stakeholder led meetings through the DC Person-Centered Thinking Learning Community and Cultural and Linguistic Competence Community of Practice. The feedback continuously informs the development of person-centered policies and procedures. The focus this quarter was on supporting direct support professionals to implement person-centered plans. | • #/% of core LTSS agencies that have implemented person-centered service protocols. |  | 2 | Revise for Year 2 - Contingent on NWD carryover funding, have person-centered thinking SME review and make recommendations on intake policies from DDS, DHCF/DCOA & DBH. For Year 3 - Each agency would have to commit to reviewing recommendations internally and with stakeholders; and then implementing where appropriate. Likewise, in Year 3, when the NWD grant has ended, each agency would be responsible for reporting their own metrics. | Year 1: Develop and recommend clear expectations and competency criteria standards for intake staff consistent with use of person-centered approaches. Year 2: Host community meetings to garner stakeholder feedback on the person-centered policies and procedures for all NWD Core LTSS agencies’ intake staff. Year 3: Finalize model policies and procedures for all NWD Core LTSS agencies’ intake staff consistent use of person-centered approaches.
|  |  | # of NWD Core LTSS intake staff that have completed person-centered training. |  | 100
Action 1.2 - Add person-centered practice standards to service planning personnel’s employee performance goals in all NWD Core LTSS agencies. | Offer training and technical assistance to NWD Core LTSS managers and staff on including person-centered standards and goals to support implementation of person-centered practices. | The NWD project team, in collaboration with DCOA, launched an interagency managers workgroup focusing on building a network of collaboration at the front door to supports and services. Relationship building is the first foundational element of a person-centered system. |  |  |  | Recommend changing goals in Year 2 & 3 because the NWD team has already created and shared PCT performance goals, standards, and competencies. For Year 2, contingent on NWD carryover funding, the NWD team will offer training for PCT supervision at the upcoming Front Door Summit. For Year 3, each agency would have to commit as to how they plan to implement these practices. The metrics have been difficult to track across agencies. Simpler metrics might be: # of DC agencies offering PCT training; # of attendees; # of sessions receiving positive participant ratings | Year 1: Develop a model of person-centered practice standards and goals that can be incorporated into employee performance measures. Year 2: Offer training and technical assistance to NWD Core LTSS managers and staff on including person-centered standards and goals to support implementation of person-centered practices. Year 3: Develop model person-centered position descriptions for NWD Core LTSS agencies’ service planning personnel.
Action #3: Develop procedures and protocols for supporting family members and others in a person’s support network to ensure that plans accurately and continuously reflect the individual’s preferences and needs. (NWD) | Develop Person Centered Planning tools to aid families in learning about person-centered practices and keeping track their family member's person-countered goals. | The NWD project team attended the national conference on Charting the LifeCourse (CtLC) to gather examples from other states on person-centered planning with family members and others in a person's support network. DDS developed a 6-month review tool using the CtLC Trajectory to factor in the perspective of family members and ensure that plans accurately respond to any changes needed to the person's preferences and needs. |  |  |  | No changes to Year 2 goal. Given the end of the NWD grant recommend changing Year 3 goal to sharing the tools developed through the public resource portal learning corner and agencies linking to it on their webpages. | Year 1: Develop Person Centered Planning Implementation Guidance in partnership with stakeholders identifying best practices for supporting families in person-centered planning for NWD Core LTSS agencies and providers. Year 2: Develop Person Centered Planning tools to aid families in learning about person-centered practices and keeping track their family member’s person-centered goals. Year 3: Use the LifeCourse Framework developed through the National Supporting Families Community of Practice, which DC participates in, to finalize policies and protocols in partnership with NWD Core LTSS agencies.
Priority Area #2: Community Engagement, Outreach and Training
Action #1: Develop and disseminate policy and protocols to increase linguistically and culturally diverse stakeholder involvement in the development, implementation and ongoing evaluation of NWD core LTSS agencies' engagement and outreach activities | Develop cultural and linguistic competency fact sheets of guiding principles for NWD Core LTSS agencies intake, outreach, and service planning personnel. | NWD has partnered with SME to review and analyze Front Door policies to determine the extent to which such policies addresses cultural and linguistic competence for NWD participating agencies. NWD/CLC subcommittee has formed a work group with co-leads from DCOA and DDS to draft guidelines on enhancing engagement to undeserved communities to be disseminated across NWD partnering agencies. | # of people reached through NWD Core LTSS agencies outreach activities |  | 125 | No change to Year 2. For Year 3, DDS will continue to lead the CLC CoP and sister agencies are welcome to participate, create action plans, and receive TA through the CoP. For Year 3, all metrics will need to be reported by participating agencies. | Year 1: Develop and finalize an assessment of linguistic and cultural competence for NWD Core LTSS agencies intake processes. Year 2: Develop cultural and linguistic competency factsheets of guiding principles for NWD Core LTSS agencies intake, outreach, and service planning personnel. Year 3: Develop model cultural and linguistic competency policies and procedures, and a cultural and linguistic framework for NWD Core LTSS agencies to support culturally and linguistically competent practices.
|  |  | # of NWD Core LTSS agencies outreach activities and resources presented in languages other than English |  | 5
|  |  | # of people reached through NWD Core LTSS Agencies' outreach activities. |  |  | This metric should be eliminated and is covered by metric 2.
Action #2: Develop mandatory training for front line staff of District No Wrong Door partner agencies about the key plans and practice changes being developed through NWD. | Update NWD Person Centered Practices training surveys to better collect participant feedback, and develop a unified survey tracking tool. | The training survey was adapted into an electronic format that can be sent to participants post-training via email. This is available for any agency to use as requested. | # of NWD Training sessions receiving positive participant rating |  | 25 | No change to Year 2 goal. For Year 3, each agency will need to identify a lead for PCT training (including registration and tracking - note that a learning platform will be available through the resource portal and is already used by DBH). | Year 1: Finalize NWD Person-Centered Practices Training for Core NWD LTSS agencies. Year 2: Update NWD Person-Centered Practices training surveys to better collect participant feedback, and develop a unified survey tracking tool. Year 3: Update NWD Person-Centered Practices Training to reflect the participant feedback and NWD practices.
Action #3: Develop a unified messaging and marketing “look” for outreach materials and replicate on all No Wrong Door partner agencies’ websites | Develop NWD webpage to be represented on all NWD Core LTSS agencies' websites. | The No Wrong Door brand will be publicized via the NWD resource portal to be launched publicly September 2018. In addition, the NWD web page is going through a revamp that will be linked to NWD agency partner’s websites. | # of website hits per month |  | 35 | Recommend changing Year 2 to the public launch of the citywide resource portal, known as DC Support Link. For Year 3, each agency would link to this on their webpage and add information on this to any new outreach materials. | Year 1: Create NWD unified marketing and branding materials for distribution. Year 2: Develop NWD webpage to be represented on all NWD Core LTSS agencies’ websites. Year 3: Assess user experience for NWD webpage to enhance NWD webpage utility.
Action #4 : Maintain and respond to inquiries at the olmstead@dc.gov e-mail address. Provide current Olmstead data online, available for public review. Host quarterly Olmstead Working Group meetings, as well as two community forums, open to the public. |  |  | # of community members attending Olmstead-related meetings/forums |  | 75
Priority Area #3: Employment
Action #2: Increase the capacity of staff across the Rehabilitation Services Administrations (RSA) through on-site training to support best practices. | Develop and implement a mentoring program for new staff to shadow and receive guidance from experience colleagues. | RSA has ensured all staff members have been trained on the PCT tools. DDS has two people on staff that support with the implementation and training for PCT tools to new staff. RSA leadership has participated in trainings and meetings to ensure the agency and the administration is continuing to grow as a PCO. The rainbow and donut exercises have been completed by all teams and are being used to ensure everyone knows all elements of the work done in the agency and to outline the roles and responsibilities for each unit as they serve people receiving our services. | # of Person-Centered Training courses completed by VR staff | 3 out of 6 Modules have been completed. | 50% | Awaiting RSA Update to include Provider training
96%
• # of people jointly served by RSA, DDA, DBH, DOES, DCPS.
• #/% of working-age people with disabilities in competitive, integrated employment.
Action #3: Increase the number of people with intellectual disabilities (IDD) and serious mental health diagnosis or serious emotional disturbance (SED) who obtain and maintain employment through better coordination of supported employment services with the Developmental Disabilities Administration (DDA) and the Department of Behavioral Health. (WIOA 1.5) | Coordinate with DBH to provide training for all VR counselors regarding mental health and substance abuse treatment services available in the District. Review the DDS Protocol regarding coordination of services between RSA and DDA, make necessary changes and provide training to all DDA Service Coordinators and VR Specialist. | RSA has designated Supported Employment Unit with 3 counselors to serve consumers with serious and persistent mental illness. There are a total of 406 active consumers with a classification of serious and persistent mental illness and the counselor's caseload size is an average of 135 consumers per counselor. RSA works collaboratively with Department of Behavioral Health (DBH) to ensure seamless referral system and coordinated service delivery by assigning evidence- based supported employment (EBSE) counselors to EBSE sites where they meet with consumers and treatment teams. During FY18, 52 clients have been employed. | # of people with serious mental health impairments (MHI) whose case is closed successfully after obtaining competitive integrated employment | 52 clients with MHI have been employed to date | 110
|  | RSA has designated Supported Employment Unit with 3 counselors to serve consumers with IDD. The number of active IDD consumers served is 215, with average caseload size per counselor at 71. RSA works collaboratively with DDA to ensure seamless referral system and coordinated service delivery by assigning evidence- based supported employment (EBSE) counselors to EBSE sites where they meet with consumers and treatment teams. Regular monthly meetings between DDA team and RSA counselors/supervisor to address case management issues pertaining to mutual RSA/DDA consumers and also scheduled to monitor the work. During FY18, 3 clients have been employed. | # of people with DD/IDD whose case is closed as successful after obtaining competitive integrated employment | 3 clients with IDD have been employed to date | 60
Action #4: Increase the number of people with intellectual disabilities (IDD) and mental health impairments (MHI) who complete training programs that prepare them for jobs in high demand fields, increasing the number of employment placements in these fields. | Coordinate with DDA and DBH to increase the number of people with IDD or MHI serviced by RSA who complete training in identified high demand industries and obtain employment in these fields | RSA and DDA have developed a streamlined approach to ensuring that individuals receiving services from DDA are able to connect with RSA seamlessly to receive support for employment. RSA and DDA have worked together to develop processes for Intake and Transition to ensure everyone who is interested in receiving services are connected to the appropriate administration. | # of people of working age supported by DDA who receive employment services from RSA. | 215 working age clients receive support from DDA and RSA | 225
|  | RSA continues to ensure that all clients are supported through the agencies that can provide them with the most support to ensure a high quality of life. RSA partners with the Department of Behavioral Health (DBH) to support clients with mental health needs as they seek employment opportunities. RSA has three counselors who co-locate with DBH to ensure we are connecting individuals to the correct services. Currently, 406 clients are receiving supports from both RSA and DBH. This number fluctuates depending on the number of active cases. | # of people supported by DBH who receive employment services from RSA | 406 working age clients receive support from DBH and RSA | 525
|  | RSA did not fund any educational or training programs tailored to people with intellectual disabilities in the first quarter of CY18. The model RSA follows for clients with IDD is a place and train model which provides on-the-job experience to clients so that they are able to successfully execute the tasks their positions require. | % increase in the number of people with intellectual and developmental disabilities (IDD) supported by RSA who complete post-secondary training programs in high demand industries | 0% increase in the number of people with IDD pursuing PSE programs | 10% | Remove -
|  | RSA has also prioritized work to support our clients with Mental Health diagnosis in connecting them with training for high demand industries. RSA has been working with the supported employment team to identify trainings that meet the high demand need and are also meeting the clients interest. Often clients pursue fields that may not be considered high demand fields for employment. | % increase in the number of people with mental health diagnoses supported by RSA who complete post-secondary training programs in high demand industries. | 0% increase in the number of people with MHI pursuing PSE programs | 10% | Remove -
Priority Area #4: Housing
Priority Area #5: Intake, Enrollment and Discharge Processes
Action 1: Develop a "person-centered profile" for use in NWD Core LTSS agencies with common information that can be collected by referral sources or state systems and shared to avoid duplication of effort | Develop a template for agency-specific data collection protocols for the common person-centered profile information. | NWD project team provided technical assistance on the person-centered profile for the implementation of the interagency case management system to ensure intake and referral workflows will enhance communication and the exchange of information in a seamless matter amongst the core partners. |  |  |  | Remove because this is encompassed by the next goal, development of CCMS, which requires DDS, DCOA and DHCF to work together on a joint intake process | Year 1: Develop a model person-centered profile for use across NWD Core LTSS agencies. Year 2: Develop a template for agency-specific data collection protocols for the common person-centered profile information. Year 3: Develop model implementation guidance on the use of person-centered profile across all NWD Core LTSS agencies.
Priority Area 6: Medicaid Waiver Management and Systems issues
Action 1: Develop the individual and Family supports Medicaid Waiver program for people with IDD who live in family homes, including services targeted to help families continue their support. | Research individuals and family support services across different jurisdiction. |  | % decrease in average length of IDD Waiver application processes for those enrolling in waiver services in DDA |  | 15% | Action item and year 2 & 3 goals are okay - but the metric does not align with the action item and should move to a DDA action item. An appropriate metric for this could be # of stakeholder engagement sessions for development of the IFS waiver | Year 1: Review pre-existing service definitions (and the feasibility of adding new services) in preparation for the HCBS waiver renewal. Year 2: Research individual and family support services across different jurisdictions. Year 3: Develop and Initiate implementation of the Individual and Family Services (IFS) waiver.
Priority Area #7: Quality of Institutional and Community-Based Services, Providers and Workforce
Action 3: Review and strength regulatory options to more effectively deal with quality issues when they arise. | Identify specific providers with deficient performance based on year one data, and take appropriate actions, including, but not limited to technical assistance or enhanced monitoring. |  | % of waiver providers that pass certification on initial provider certification review (PCR) |  | 80%
|  |  | % of people who receive the services for which they have been approved/authorized | (97%) 157/162 | 80%
|  | At the end of 2017, a total of 34 people were found to receive day habilitation services in facility-based settings. DDS will report on this measure annually to determine compliance with the goal of a 10% decrease from the 2017 total, and will provide a quarterly update to review progress towards this goal. | % decrease in number of people receiving supports from DDA in facility-based day programs (for those spending 4 or more days per week in a day facility) | Q1 2018: (0) All people are receiving day habilitation services below the established threshold (30 hours a week or more). | 10% | Recommend changing this to an annual measure. During the ISP planning meetings held annually (except in the case of a change in support needs requiring a service amendment) services are typically authorized for the duration of one year. As a result of this process, the percent decrease is better suited for being observed at the beginning of each year as opposed to each quarter. However, staff still plan to monitor these data internally in a quarterly basis.
Action 4: Review all providers' Language Access plans to ensure residents with limited English proficiency have access to linguistically and culturally appropriate services. | Analyze data from the provider review tools (completed annually) to verify that all providers have Language Access plans and policies in place ensuring residents with limited English proficiency have access to linguistically and culturally appropriate services.
Priority Area #8: Supporting Children and Youth
Action #1: Develop an inter-agency plan to ensure that students with disabilities who graduate with a certificate (rather than a diploma), have at least one community-based, integrated paid work experience prior to school exit. | Finalize MOAs with all schools that have identified students on certificate track to ensure coordination of services to provider for work-based learning experiences prior to exit from school. Collaborate in development of internship/worksites to provide work experiences. | RSA was able to provide pre-employment transition services to 574 students in the first quarter of CY18. In total for SY17-18, 1,870 students have received at least one pre-employment transition service. This is out of a total of 3,352 students that could potentially receive pre-ETS. RSA is in the process of updating our MOA's and MOU's with District LEA's and OSSE to not only maintain our Pre-ETS progress, but to build capacity to ensure the provision of those services to 14 and 15 year olds beginning in 3rd quarter 2018. | % of students with IEPs or 504 plans receiving at least one PreEmployment Transition Service each school year | 56% of students with an IEP or 504 plan are receiving or have received a Pre-Employment Transition Service | 80%
|  |  | % of students with disabilities that have a community-based. Integrated paid work experience | 221 students are receiving or have received a community-based, integrated paid work experience | 75
Action #2: Increase the timely submission and completion of applications for adult DDA services for children with IDD who are out of state residential facilities. | Work closely with DCPS to improve the timely and accurate processing of comprehensive applications, including the submission of all relevant diagnostic documentation |  | • #/% of students with IEPs or 504 Plans receiving at least one Pre Employment Transition Service each school year |  | 85%
• #/% of students with disabilities that have a community-based, integrated paid work experience
Action 3: Develop NWD Person-Centered Practices curriculum and train Mentor Trainers to deliver the training to NWD Core LTSS agencies and community Partners | Work with various accreditation bodies to offer CEU cred for professional staff who attend NWD PCT training. | Obtained CEU credits for social workers and nurses. Conducted 2 RN-Focused trainings this quarter. |  |  |  | No change to Year 2 goal. For Year 3, host this information on the Resource Portal, rather than on a NWD specific webpage. | Year 1: Offer NWD PCT training to government and provider staff and community partners at least 10x/ year. Year 2: Work with various accreditation bodies to offer CEU credits for professional staff who attend NWD PCT training. Year 3: Create a PCT section of the NWD webpage that includes PCT resources, including tools and webinars.
Priority Area #9: Wellness and Quality of Life
Action #2: Identify ways to give people with disabilities and older adults in the District of Columbia better access to multiple transportation services, allowing for greater mobility with dignity and independence, and easier integration in the community. | Establish working group of partner agencies to meet regularly and implement short-term recommendations and identify funding for long term recommendations of the accessDC study |  | • #/% of inclusive daytime program offerings. |  | Baseline
|  |  | # of people with disabilities using at least 2 transportation services for which they are eligible. |  |  | Recommend deleting this measure. DDOT (as the main agency responsible) is using their own system for tracking and reporting these transportation data. These metrics do not align with the goal. If we want to keep the metric on inclusive daytime programs offered by DC agencies, we should change the goal and ensure involvement of DCPL and DPR.